## Slide 1: Metal - an agile scrum project
By: Jay Kishan Sahu Date: 4/23/2025

## Slide 2: Situation
The METal (Manage and Engage Talent) application is integral for managing requisitions, candidate sourcing, and client-vendor interactions in the recruitment lifecycle.
Integrated with platforms like Monster, CareerBuilder, Sovern, and Workflow for end-to-end hiring processes.
Used by multiple roles: Recruiters, Delivery Managers, Account Managers, and the TAG team.

## Slide 3: Problem
Manual and redundant data entry points reduce operational efficiency.
Limited visibility across stakeholders due to inconsistent reporting and tracking mechanisms.
Integration complexity with third-party tools leading to delayed updates and errors.

## Slide 4: Opportunity
Streamline the end-to-end recruitment process with enhanced usability and automation.
Improve system integration with third-party tools for real-time updates.
Boost candidate redeployment effectiveness through improved TAG team workflows.

## Slide 5: Purpose statements
To enhance the METal application by improving system integration, streamlining candidate and requisition management workflows, and enabling better stakeholder collaboration through Agile Scrum methodology.

## Slide 6: Project Activities
Requirement elicitation from stakeholders.
User story creation and grooming.
Sprint planning and execution.
UI/UX enhancements for candidate/requisition screens.
Integration improvements with Sovern, Workflow, and VISITe.
System testing and feedback cycles.

## Slide 7: Success Criteria
Specific: Reduce requisition processing time by 30%.
Measurable: Improve integration response time to under 5 seconds.
Achievable: Implement 10 high-priority user stories per sprint.
Relevant: Align features with the needs of recruiters, DMs, and TAG team.
Time-bound: Complete all enhancements in 4 sprints (8 weeks).

## Slide 8: Methods
Agile Scrum framework with 2-week sprints.
Daily stand-ups for progress tracking.
Sprint reviews with stakeholders for continuous feedback.
Retrospectives to refine team processes.
JIRA for backlog and sprint management.

## Slide 9: approach
Issue is discovered and reported by key users (Recruiters, DMs, TAG team).
Prioritize backlog items based on business impact.
Deliver incrementally through MVP-focused sprints.
Continuous integration and validation of new features

## Slide 10: Resources
Product Owner – Dakshesh
Scrum Master – Paresh
Business Analyst – Jay Kishan
Developers – Gunjan, Puneet, Bala
Testers – Vihana, Vipul
Stakeholders – Recruiters, Delivery Managers, TAG team, SD team

## Slide 11: Risks and dependencies
Risks:
      Resistance to change from users.
      Delays in API responses from integrated systems.
      Misalignment in stakeholder expectations.
Dependencies:
      Data from Monster, CES, CareerBuilder.
      Sovern and Workflow API availability.

## Slide 12: Executive Summary
This Agile Scrum project aims to elevate the METal application’s efficiency, accuracy, and usability by resolving current integration challenges and enhancing workflows. With clear SMART goals, a cross-functional team, and iterative delivery, the project is poised to significantly improve recruitment operations and stakeholder satisfaction.