## Slide 1: Project Title: Neuria
Prepared By: Nikita Shivaji Suryawanshi
Date: 12/03/2025

## Slide 2: Situation
Neurological conditions, such as Parkinson’s, Alzheimer’s, epilepsy, and multiple sclerosis require specialized treatment and continuous monitoring by physicians.
Many patients struggle to find the right specialists, and doctors lack a unified platform to manage patient care efficiently.
With advancements in digital health, there is an opportunity to leverage technology to improve patient-doctor interactions, treatment tracking, and overall healthcare accessibility.

## Slide 3: Problem
Limited Access to Specialists: Patients often face difficulties in locating and reaching the right neurological specialists.
Inefficient Treatment Tracking: Physicians lack an integrated system to monitor and manage patients' progress.
Fragmented Communication: There is no centralized platform for doctors to collaborate, share insights, and provide personalized care.
Lack of Digital Presence for Physicians: Many neurologists do not have a streamlined way to present their credentials, availability, and expertise.

## Slide 4: Opportunity
Develop an app for physicians that allows them to manage their profiles, list their expertise, and connect with patients.
Provide real-time tracking and progress monitoring for neurological treatments.
Enable appointment scheduling and teleconsultation features for better patient accessibility.
Create a collaborative network for physicians to discuss complex cases and advancements in neurological treatment.

## Slide 5: Purpose Statement (Goals):
The purpose of this project is to design, develop, and implement a digital platform that enhances neurological condition treatment by connecting patients with specialized physicians.
The platform will provide a centralized database of doctor information, facilitate seamless communication between doctors and patients, and offer tools for treatment tracking, appointment scheduling, and teleconsultation.
This initiative aims to improve healthcare accessibility, optimize patient care, and foster collaboration among medical professionals.

## Slide 6: Project Objectives:
Ensure data security and compliance – Integrate security measures and ensure compliance with healthcare regulations (Ex. HIPAA)
Solution selection according to design criteria, specifications, and requirements – Identify and finalize a technology stack and system architecture that meets the needs of physicians and patients.
Develop a centralized physician database – Create a structured database of neurological specialists with their qualifications, expertise, and availability.
Enable patient-physician interaction and treatment tracking – Implement features for appointment scheduling, teleconsultation, and progress tracking for neurological conditions.
Solution prototyping and testing – Develop a prototype of the application, conduct usability testing, and refine based on feedback.

## Slide 7: Success Criteria:
Enhance patient-doctor connectivity – Provide seamless appointment scheduling, teleconsultation, and communication features to improve accessibility for patients.
Increase physician engagement and adoption – Ensure a user-friendly interface that encourages doctors to use the platform for managing their practice and collaborating with peers.
Ensure data security and compliance – Maintain compliance with healthcare regulations (HIPAA, GDPR) to safeguard sensitive medical information.
Reduce system downtime and improve response times – Implement a robust infrastructure to minimize system downtime, enhance performance, and optimize the platform's speed.

## Slide 8: Methods/Approach:
Waterfall methodology- This model follows a structured approach with each phase having specific deliverables. This model works on smaller project works well for smaller Project where requirement are very well understood.
Requirement gathering- Where the elicitation technique have been applied like brainstorming, Focus Grouping observations, JAD Session for requirement gathering, Use case Specification.
Requirement Analysis- Do stakeholder analysis (RASCI Matrix), sort requirements and prioritize requirements, Made use case diagrams.
Design- Once requirement analysis done we move forward on Design stage. In this stage we made Prototype, Activity diagrams, Create architecture, database schema. In this stage DB architecture uses persistence classes and come up with ER Diagram and DB Schema. GUI Designer will look into transient class and design all possible Screens.

## Slide 9: Methods/Approach:
Development- In this Phase organize JAD session and clarify queries of technical team during coding, Update End user manuals, developers refers diagram for development.
Testing- In this stage prepared Test cases from use cases, performs high level testing, prepare clients for UAT and update RTM. Take signoff from client.
Deployment and Implementation- Forward RTM to client or the which should be attached to the Project closure documents. Coordinate to complete and share End user Manuals, Plan training session for end user and prepared Lesson learned from project.

## Slide 10: Resources:
People- Project Team Members: Business Analysts, Neurologists, UX/UI Designers, Software Developers, QA Engineers, Project Managers, IT Support. Product Owner and Data Curation team have the experience in Medical and Healthcare Domain.
Time- This Project comes under Waterfall Methodology so budget and time is fixed for this project.
-Estimated project timeline: 12 months.
Requirement Gathering & Planning: 2 months
Design & Development: 7 months
Testing & Training: 2 months
Deployment & Go-Live: 1 month

## Slide 11: Resources:
Budget - Total Estimated Budget: Rs. 9,500,000
Development Costs: Rs. 50,00,000
Hardware & Infrastructure: Rs. 1,000,000
Software & Licensing: Rs. 1,000,000
Training & Support: Rs. 15,00,000
Marketing & Launch: Rs. 1,000,000

## Slide 12: Risk
Adoption Resistance by Physicians – Doctors may be reluctant to switch to a new platform due to existing workflows and familiarity with current systems.
Regulatory Compliance Challenges – Ensuring adherence to healthcare regulations (HIPAA, GDPR) may require additional legal and technical efforts.
Data Security and Privacy Risks – Storing and transmitting sensitive patient information introduces risks of data breaches and cyberattacks.
Technical Downtime and Maintenance – Unexpected technical failures or system downtime can impact patient care and physician workflows.

## Slide 13: Dependencies
Availability of Skilled Medical Experts – The success of the project depends on collaboration between neurologists, healthcare professionals and their availability.
Regulatory Approvals and Compliance – The project must comply with healthcare laws and data protection regulations before launch.
Stable Internet & Infrastructure Support – A reliable cloud environment and IT support are necessary for smooth operations.
Patient Engagement & Adoption – The success of the platform depends on patients actively using the system for appointments, treatment tracking, and consultations.
Multi-Device & OS Compatibility – The app must work smoothly across different devices (smartphones, tablets, desktops) and operating systems (iOS, Android, Windows).