## Slide 1: CERT ISSUE
PREPARED BY: VENKATESH DHANANA
DATE: 28-04-2025

## Slide 2
Situation: Patra India Pvt. Ltd. has been manually creating “Insurance Certificates” for clients in the united states for the past five years. they receive insurance-related details via email and use a manual tool to prepare and deliver certificates for various types of insurances like houses, vehicles, human life, construction projects and other small and large businesses.
Problem:
High Risk of Human Errors: Manual data entry is leading to typographical mistakes in certificates.
Delays in Certificate Issuance: The manual process causes delays in processing and delivering certificates to clients.
Missed Communications: There are instances where client emails are missed or overlooked, resulting in missed deadlines and client dissatisfaction.
Scalability Issues: As the number of clients and requests grow, the manual process struggles to keep up efficiently.
Opportunity:
Automation of the Certificate Creation Process: Implementing an automated solution can drastically reduce manual errors and processing times.
Improved Client Satisfaction: Faster and more accurate delivery of certificates will enhance client trust and satisfaction.
Efficient Email and Task Management: Automated email tracking and data extraction can ensure no client request is missed.
Operational Scalability: Automation will allow Patra India to handle larger volumes of requests without proportionally increasing workforce costs.
Competitive Advantage: Streamlining operations can position Patra India as a more reliable and modern service provider compared to competitors still using manual processes.

## Slide 3
Purpose Statement:
The purpose of the Cert Issue project is to automate the end-to-end process of receiving client requirements, creating insurance certificates and delivering them efficiently, accurately and timely.
The project aims to:
Eliminate manual errors by automating data entry and certificate generation.
Reduce turnaround time for issuing certificates to clients.
Ensure no client requests are missed by automating email tracking and notifications.
Enhance operational efficiency and enable the company to manage increasing client demand without additional manual effort.
Improve client satisfaction through faster, error-free and reliable service delivery.
Provide a scalable solution that supports future business growth and increased volumes.
Establish Patra India Pvt. Ltd. as a leader in efficient, technology-driven insurance certificate processing.

## Slide 4
Project Objectives:
Automate Certificate Creation: Design and implement a system to automatically generate insurance certificates based on client-provided data.
Automate Email Processing: Develop functionality to automatically retrieve, read, and extract key information from client emails without missing any requests.
Ensure Data Accuracy: Minimize typographical and manual errors by integrating validation and verification mechanisms during data processing and certificate creation.
Reduce Turnaround Time: Achieve faster issuance of certificates by reducing dependency on manual operations.
Enhance Monitoring and Tracking: Provide a dashboard or tracking system to monitor incoming requests, processing status, and delivery timelines.
Improve Client Communication: Send automated acknowledgments and delivery confirmations to clients to keep them informed throughout the process.
Provide Scalable Architecture: Build a solution that can handle increasing volumes of certificate requests without degrading performance.
Implement a Robust Testing Mechanism: Ensure the system is thoroughly tested to handle various types of insurance certificates and business scenarios.
Training and Change Management: Train Patra India employees on using the new automated system effectively and manage the transition smoothly.

## Slide 5
Success Criteria:
Error Rate Reduction: Manual data entry errors are reduced by at least 90% compared to the current process.
Turnaround Time Improvement: The average time to issue a certificate is reduced by at least 50% after automation.
100% Email Processing: All client emails requesting certificates are captured, processed, and responded to without any missed communications.
Certificate Accuracy: Generated certificates match client requirements with 100% data accuracy as validated by automated checks and manual audits.
Client Satisfaction: Client feedback surveys show an improvement in satisfaction by at least 30% within the first six months after implementation.
System Uptime and Availability: The automated system maintains at least 99% uptime to ensure continuous service availability.
Scalability: The system can handle at least 2x the current volume of certificate requests without performance degradation.
Regulatory and Compliance Standards: All insurance certificates are generated in compliance with relevant regulatory standards and client-specific guidelines.
Project Delivery on Time and Budget: The project is completed within the agreed timeframe and budget, meeting all major deliverables.

## Slide 6
Waterfall Method/Approach:
The Waterfall model is a linear and sequential approach where the project progresses through distinct phases. Each phase must be completed before the next begins, and there is typically no overlapping between phases.
1. Requirement Gathering and Analysis:
Collect detailed requirements from Patra India’s business stakeholders.
Understand the data fields required for certificates (vendor details, insurance type, dates, nominee details, etc.).
Document all functional and non-functional requirements.
Define clear acceptance criteria and success factors.
Deliverable: Requirements Specification Document (RSD)
2. System Design:
Create the system architecture based on requirements.
Design the database structure for storing certificate data.
Design interfaces for email extraction, certificate creation, and client notifications.
Prepare system flow diagrams, use case diagrams, and activity diagrams.
Deliverable: System Design Document (SDD)
3. Development:
Develop modules for:
  Email extraction and parsing
  Automated certificate generation
  Data validation and error handling
  Certificate delivery (email or portal upload)
Backend development using Java technologies.
Deliverable: Fully coded and internally tested modules

## Slide 7
4. Testing:
Perform unit testing, integration testing, system testing and user acceptance testing (UAT).
Test different types of insurance certificates to ensure comprehensive coverage.
Validate accuracy, performance and email handling.
Deliverable: Testing Report and Bug Fixes
5. Deployment:
Deploy the solution in the production environment.
Ensure secure email integration and certificate storage.
Deliverable: Live, working automated system
6. Maintenance and Support:
Provide post-deployment support for bug fixes, performance tuning, and minor enhancements.
Monitor system performance and handle any operational issues.
Deliverable: Maintenance logs, Updates, and Support documentation
Key Characteristics of Waterfall in This Project:
Clear structure: Each phase is well-defined and documented.
Minimal changes during development: Requirements are expected to be stable and frozen before design and coding begin.
Heavy documentation: Essential for clear understanding between Patra India and IT Solutions Pvt. Ltd.
Ideal for predictable projects: Since the process of certificate generation is known and repeatable.

## Slide 8
Resources for Cert Issue Project
1. People (Human Resources):
From IT Solutions Pvt. Ltd.:
Project Manager (1) - Oversees project execution, timeline management, client coordination.
Java Developers (5) - Responsible for coding backend logic, email automation, certificate generation modules.
Database Administrators (DB Team) (2) - Design and manage databases to store certificate data securely.
System Administrators (Admin Team) (2) - Set up servers, manage deployment environments, ensure system security and availability.
Testing Team (QA Testers) (3) - Conduct unit testing, integration testing, system testing and user acceptance testing (UAT).
Business Analyst (Me) – Gathering requirements, documentations, conducting UATs, supporting in go live and maintenance.
From Patra India Pvt. Ltd.:
Business Stakeholders (2–3) - Provide business requirements, validate deliverables and participate in UAT.
Process Experts/Current Users (2–3) - Help document current manual processes and test the new automated system.
2. Time (Timeline):
Estimated Total Project Duration: 7–8 months
Requirement Gathering and Analysis - 1 month
System Design - 1 month
Development - 3 months
Testing - 1–1.5 months
Deployment and Go-live - 0.5 month
Support and Stabilization - 1–2 months post-deployment

## Slide 9
3. Budget:
Estimated Budget Components:
Development Costs: Salaries for BA, Java developers, DB admins, testers, project manager and others.
Infrastructure Costs: Servers, backup systems, cloud storage.
Licensing Costs: Software licenses (if any email automation or document generation tools are used).
Training Costs: Training sessions for Patra India employees on the new system.
Support and Maintenance Costs: 1–2 months of post-deployment support.
Rough Budget Range (Indicative):
35–45 Lakhs INR (depending on tools, infrastructure and duration) – This is rough estimation.
4. Other Resources:
Hardware:
Dedicated servers for hosting the application and database
Backup and disaster recovery systems
Software:
Development tools (Java IDEs, Database tools)
Automated email parsing tools
Certificate template design tools
Network:
High-speed internet connections
VPNs or secure email gateways for handling client data securely

## Slide 10
Risks and Dependencies
Risks:
Incomplete or Changing Requirements: If Patra India's business stakeholders are not clear or if requirements keep changing during development, it could delay the project.
Email Format Variations: Clients might send data in different email formats, making it difficult to automate email parsing accurately.
Technical Complexity: Integration of email systems with automated processing may face technical hurdles (e.g., attachments, image-based emails).
Data Security Risks: Sensitive client and insurance data could be exposed if strong data security measures aren't implemented.
User Resistance: Employees used to manual processes might resist adapting to the new automated system, affecting adoption rates.
Testing Gaps: If comprehensive testing is not performed, errors could still creep into certificate generation, damaging client trust.
System Downtime: If the automated system faces technical failures post-launch, it could halt certificate issuance and impact client relationships.
Budget Overruns: Scope creep, unforeseen technical challenges or extended development time could lead to exceeding the initial budget.
Vendor Email Delays: Clients might delay sending their data emails, affecting the daily workflow, although this is not system-related, it impacts overall performance metrics.
Compliance Risks: Failure to meet U.S. insurance document regulatory standards could result in legal issues.

## Slide 11
Dependencies:
Client Email Inputs: The automation process relies on timely and structured data from client emails.
Business User Availability: Business experts from Patra India must be available for requirement gathering, clarifications, and UAT (User Acceptance Testing).
Infrastructure Readiness: Servers, networks and environments must be ready before deployment and testing can proceed.
Third-Party Tools: If any third-party email parsers, document generation tools or security tools are used, their availability and integration must be reliable.
Management Approvals: Timely approvals are needed at various stages (requirements sign-off, design sign-off, UAT sign-off) to avoid project delays.
Training Completion: Successful training of Patra staff is essential before full system rollout to ensure smooth transition and minimize errors.
Legal and Compliance Review: Any automated certificate generated must be reviewed to ensure compliance with insurance regulations and client agreements.

## Slide 12
Thank You !