## Slide 1: Project-HrOne
Project Title : My SpineHR | 
Prepared By : Tejas Yadav | Date : 29/12/2024

## Slide 2: Situation
As a startup currently HR are using a paid software for Employee management.
We are no more a Small size company.
We want a self-oriented and sustainable HR management software.
We are concern about the employee data to get leak.
Third party charges are expensive to pay and it’s increasing every year.

## Slide 3: Current Problems
We are unable to track the daily shift timing of every employee.
We are unable to track the productivity hours of every employee.
We are unable to feed the employee Data in Server.
Lack of centralized data for employee records.
Manual processes causing delays and errors.
We are manually updating every employee’s data in every profile.
We are unable to set the Hierarchy for every department.
We are unable to calculate salary on time due to less accurate data and manual updates.
We are facing issues to upload documents on server.
We are unable to update the system with labor laws.
Employees are unsatisfied by current HR management system and having bad user experience.

## Slide 4: Opportunity
Addressing existing inefficiencies.
Enhancing employee satisfaction and performance tracking.
Meeting organizational goals and compliance requirements.
A robust system supporting HR operations and driving employee engagement.

## Slide 5: Project Background
Manual HR management practices prevalent for over 3 years.
Increasing workforce complexity due to company growth over the years.
Project helps to Streamline operations aligns with company’s growth strategy.
Project supports compliance and improves organizational efficiency.

## Slide 6: Proposed Solution
Create a centralized Database.
Tracker for Attendance, leaves, performance and productivity.
Tools for generating of daily, weekly and monthly reports.
Automate Payroll process.
Real-time analysis for better decision making.
Employee self-service portal.

## Slide 7: Purpose Statement (Goals)
Automate daily, weekly and monthly HR processes.
Enhance employee engagement.
Ensure compliance with every labor laws.
Provide actionable insights through analytics.
Reduce payroll processing time by 50% within 3 months.
Achieve 90% employee satisfaction with the new system within 1 year.

## Slide 8: Project Objectives
User friendly design and easy to understand.
Increase HR’s operational productivity.
Track attendance and daily productivity of employees.
Automate daily, weekly and monthly insight analysis.
Enhance employee engagement.
Streamline recruitment workflows.
Centralized employee data on server.
Tracking of leaves and performance of every employee.
Automate payroll process.
A manual how to operate software and a feedback from to improve any bugs or error.

## Slide 9: Success Criteria
Fully functional Employee HR Management System.
User training and support documentation.
Reduction in manual errors by 80%.
Employee self-service adoption rate of 85%.
System uptime of 99.9%.
Increase in HR operation process by 90%.
Fully automate payroll process.

## Slide 10: Methods / Approach
Requirement Gathering and Analysis :
  Conduct interview with SME and surveys to gather requirements.
  Document Functional and Business Requirement.
Solution Design and Selection :
  Finalize Web page and Applicaiton modules as per requirements.
  Finalize the solution design and configuration plan in consultation with stakeholders.
Prototyping :
  Demonstrate the prototype to key users for feedback and validation.
  Make iterative improvements based on feedback.
Testing and Quality Assurance:
  Perform unit, system, and user acceptance testing (UAT) to ensure functionality and reliability.
  Address all issues and validate fixes before the live phase.
Training and Change Management:
  Develop user manuals, guides, and training materials tailored to various user groups.
Deployment and Implementation:
  Execute the full deployment.
  Provide real-time support during the transition to the new system.
Performance Review:
  Provide real-time support during the transition to the new system.

## Slide 11: Required Resources
Estimate Budget : $40,000
Timeline : 6 Months
People : ($30,000)
  Project Manager, Business Analyst, HR Team(SME), Developer Team, external consultants.
Software :
  Software licenses: $500.
  Implementation and training: $3000.
Tools and Technology: ($6000)
  Cloud-based solutions (e.g., AWS).
  Website and Applications.
  Server Systems and Computers.
  Collaboration tools for training and communication (Video tutorials, PPTs, Recorded training sessions).

## Slide 12: Risks and Mitigations
  Resistance to Change :
    HR team may not accept the developed system.
    Continuously asking for changes.
  Budget overruns :
    Regular budget reviews and stakeholder updates.
  Data security breaches :
    Robust encryption and access controls.
  Third party server :
    Dependencies on third party server.

## Slide 13: Timeline
  Month 1-2: Requirement Analysis and System Design.
  Month 3-4: Development and Testing.
  Month 5: Deployment and User Training.
  Month 6: Monitoring and Feedback.

## Slide 14: Conclusion
A comprehensive Employee Management System addresses HR inefficiencies, enhances employee satisfaction, and aligns with business objectives. Despite operating on a tight budget, system offers an efficient solution to streamline operations for both HR and employees.
Key benefits include:
  Automated tracking of attendance and employee performance, enabling the HR team to focus on strategic priorities and reducing operational costs.
  Individual performance tracking for employees, boosting motivation and productivity.
  A secure platform for employees to update personal documents directly, minimizing the risk of data breaches and safeguarding sensitive information.
This system ensures seamless functionality and supports the organization in achieving its operational goals effectively.

## Slide 15
To be Completed by Partoshtam D. | 
GuruImpact techo. Project Sponsor | Parshotam D. Project Manager