# Capstone Project 1 (Part1/3)

## Online Agriculture Product Store

#### Question 1: Identify Business Process Model for Online Agriculture Store – (Goal, Inputs, Resources, Outputs, Activities, Value created to the end Customer)

Answer: Business Process is a collection of activities designed to produce a specific output for a particular customer or market. A business process model is a model with specific ordering of work activities across time and place with a beginning and end and clearly defined inputs and outputs with required resources.

Goal: To provide a platform for the farmers in remote areas with a web or mobile application to access, provide information, purchase agricultural products (seeds, fertilizers, pesticides) directly from the manufacturers and receive them at the farmer location

Inputs:

- Internet connectivity (for Web and Mobile applications)

- Product information – Details from Manufacturers about fertilizers, seeds and pesticides.

- Farmer requirements – required product type, quantity, delivery location

- Vendor registration – Manufacturer registration and details of business

- Farmer Registration – Individual farmer registration with details of address and contact

- Logistics Information – data from delivery partners for order tracking

- Payment details – payment details from farmers regarding payment online, card, or Cash on delivery.

Resources:

- IT platform

- Databases

- Project team & management

- Ben, Peter and Kevin as shareholders

- Time – 18 months

- Budget – 2 Crore

- Vendor management and partnership with manufacturers and suppliers for product listing on website.

Outputs:

- Bill Generation – Bill and invoice generation of the transactions and saving for future reference.

- Farmer Accounts

- Vendor Accounts

- Payment Screens

- Order details

- Tracking of order (Delivery partner details, Order Status)

- Order delivery – complete payment and order delivery confirmation. Delivery of Fertilizers, Seeds, Pesticides to the farmer location

Activities:

- Farmer to be able to create their own profile and log in with their credentials.

- Vendors to list all of his products (Fertilizers, seeds and Pesticides) on the vendor profile created.

- Farmer to search for the product listings by the vendors and should be able to select and view details of the product chosen.

- Farmer will then add to cart, his required products, and Go to the payment page

- Farmer will pay using his Net banking, Cash on delivery, Debit, credit or UPI payment.

- Vendor will be confirming the payment and give order confirmation to the farmers

- Vendors will arrange for delivery of the ordered products through logistics support and intimate the same to the farmer

- Delivery services provider will deliver the goods to the farmer at their location

- A dedicated customer support system will help the team to track the issues or enquiries raised by farmers or vendors regarding the orders or products.

- Farmers to be able to provide feedback to the vendors regarding the product, service delivery and experience.

Value created to the end users:

- Increased Accessibility – easily accessible agricultural products with a wide variety

- Cost savings – Direct interactions with the manufacturers will make it more cost beneficial by reducing the distributors and supplier costs. Cost saving will also be possible because of competitive pricing

- Increased exposure to goods – Farmers would be getting a wider exposure to multiple goods that they may have missed earlier due to limited reach in local vendors.

- Reduced Time of procurement – Farmers can reduce the time of procurement by planning the agricultural products in advance and get it delivered in time.

- Better usability of goods – The app will make it easy for the farmers to make informed decisions by being able to understand details of each and every product and then choose a right agricultural product match for themselves.

#### Question 2: Mr. Karthik is doing SWOT analysis before he accepts this project. What Aspects He Should consider as Strengths, as Weaknesses, as Opportunity and as Threats.

Answer:

Strengths

- Mr. Henry has been a successful businessman. Thus, his experience will prove to make the project a success. He will be able to understand the technical aspects of the business and bring better understanding

- Mr. Pandu from SOONY company is a Finance head involved along with Mr. Henry who must’ve helped Mr. Henry in becoming a successful Businessman. His expertise would also be a strength

- A financially stable project since a budget of 2 Cr has already been allotted.

- The experienced human resources dedicated for this project will prove to be helpful in development

- Support and inputs from Stakeholders like Peter, Kevin and Ben will help in refining the application and making it more suitable for end user.

Weaknesses

- Agriculture E-Commerce platform would not prove to be an expertise for APT’s prior experience.

- Handling apps and using smartphones with internet may be a weakness for farmers.

- Logistically, delivery to remote areas is difficult.

- Network connectivity in remote areas may be slow and poor

Opportunities

- Growing use of Smartphones by farmers. The app expects usage of internet and mobile application to farmers. This will help increased usage of internet and ecommerce in remote areas for farmers.

- Agricultural Product online software is an untapped market and may open a lot of new aspects of business.

- This will also be an addition in Digital India Initiative.

- This can also open aspects to sell products like Irrigation tools, farm equipment, etc.

- This app is being promoted as a CSR initiative. Thus promoting more on social impact and not on just profits.

Threats

- There's a risk that farmers may be resistant to adopting new technology or may prefer traditional purchasing methods, impacting the platform's user base.

- Cyber threats may affect the trust of the farmers and may reduce the use of the app

- The project relies on internet connectivity and mobile access in remote areas, which might be unreliable. There would be need to account for users who may not have smartphones or limited technical literacy.

#### Question 3: Mr Karthik is trying to do feasibility study on doing this project in Technology (Java), Please help him with points (HW SW Trained Resources Budget Time frame) to consider in feasibility Study.

Answer:

Feasibility study is the study of practicality of any project.

- Hardware (Equipment Needed)

- Basic servers or cloud storage to run the website and mobile app.

- Internet connectivity for smooth functioning.

- Farmers will mostly use simple smartphones, so the system should work well even on low-cost devices.

- Companies (manufacturers) will access through computers or mobiles.

- Software (Programs Needed)

- The main application will be developed in Java, a widely used and reliable language.

- A website for companies and farmers to access.

- A mobile app for farmers (since many rely on smartphones).

- A database to store product and order details.

- A payment system for digital transactions (UPI, wallet, card).

- Security features to keep payments and farmer data safe.

- Trained Resources (People Needed)

- Project Manager – oversee project progress.

- Business Analyst (BA) – gather requirements from farmers, companies, and committee.

- Developers – build the website and mobile app.

- Database & Network specialists – maintain data and ensure connectivity.

- Testers – check the application works correctly before release.

- Support Team – provide help to farmers after launch.

- Budget (₹2 Crores)

- Setting up servers and technology.

- Salaries for project team.

- Training for farmers on how to use the app.

- Marketing and awareness in rural areas.

- Ongoing support and maintenance.

- Time Frame (18 Months)

- Planning & Requirement Gathering – 1–2 months.

- Designing the System – 2 months.

- Development (building website + app) – 6–7 months.

- Testing – 2–3 months.

- Final Launch & Support – 2 months.

#### Question 4: Mr. Karthik must submit Gap Analysis to Mr. Henry to convince to initiate this project. What points (compare AS-IS existing process with TO-BE future Process) to showcase in the GAP Analysis

Answer:

Gap Analysis is the study or the process of identifying the difference or ‘gap’ between the current ‘As Is’ state, and the future desired ‘To Be’ state.

AS IS:

- Farmers are unable to procure seeds, fertilizers and pesticides for farming purposes. They need to travel long distances in order to procure them. Also, they may, or may not receive the needed products because of availability

- The dependency of farmers is more on the vendors whom they buy the products from. And thus they may not be fully aware of the product process, available options, better products, etc. They may not be knowing about the quality, alternatives available as well. They have to be dependent on the seller for the prices and product information. There is no conversation between the farmers and the manufacturers.

- The farmers may have to be dependent on cash options only for the payment.

- They may not be knowing waiting time of when the products would actually reach them.

TO BE:

- Farmers will be able to browse between the products needed from the website or app at the comfort of their house and this will be reducing the travel cost.

- They will be aware of the availability of the products online before ordering and also the wait time, if they are ordering it for later.

- The products would be listed from the manufacturers directly, thus leaving no gaps in conversations between the farmer and the manufacturers. Also, getting full details of the product on the fingertips.

- Reducing time and cost of travel of the farmers.

- More payment options like card, wallet, UPI or cash on delivery.

- They will be able to track the delivery status at the said point in time from their purchase.

Gap Analysis:

- Currently the entire process is physical. The future system is going to be completely digital with a better scope.

- The system currently has a lot of concerns regarding delivery, availability, etc. The system to be designed will make the process digital and easy for use. The system would also be more transparent.

- The current system does not provide complete details of the product. The future system will provide details and increase the productivity of the farm by use of efficient products.

- The transparency will increase with involvement of manufacturers directly and not involving the middlemen.

- The reducing of time of delivery will also help the availability of goods as per the requirement of the farmers.

- The mode of payment will increase the use of digital payments.

- Bridging this gap through the Online Agriculture Store will save farmers’ time, reduce costs, increase transparency, and improve productivity.

#### Question 5: List down different risk factors that may be involved (BA Risks and process/Project Risks)

Answer:

BA Risks:

- Gathering Requirements from the farmers because of the communication gap

- The technical expertise may not be there with all farmers and thus might not give a perfect analysis or requirements.

- If requirements are not clear, the final project may be at a risk

- Communicating and dealing with all stakeholders and matching their expectations.

- Having a project that will not be user friendly

- Conflicts between the teammates

Process/Project Risks:

- Delay in project because of increase in requirements at a later stage.

- Completing the Project in 18 months

- Limited Budget

- Difficulty in reaching out to remote areas and farmers onboarding

- Educating each farmer to use the Application

- Language and User Interface Barrier to communicate properly with the end user.

- Handling payment gateways efficiently without any hassle because farmers would not easily trust on to the new process of online payments.

- The app not being user friendly.

- Changing market scenarios and availability of existing online platforms.

#### Question 6. Perform stakeholder analysis (RACI Matrix) to find out the key stakeholders who can take Decisions and Who are the influencers

Answer:

Stakeholder Analysis is the process of identifying and understanding individuals or groups who can affect or ae affected by the project. The technique to be used here is RACI Matrix. It stands for understanding R – Responsible, A – Accountable, C – Consulted, I – Informed.

To start with the process, firstly, it is important to understand the stakeholders.

- Mr. Henry – The main sponsor of the project from SOONY.

- Mr. Pandu – He would be the Financial Head of the project.

- Mr. Dooku – working as the Project Coordinator.

- Peter, Kevin, Ben – The farmers who would be acting as the end users of the product.

- Vendors and Manufacturers – Who would be listing their products on the website

- Mr. Karthik – he from APT IT is the delivery head of the project

- Mr.Vandanam – working as the project manager

- Development and testing team – from APT IT who would be developing the software

- Business Analyst – who would be involved in the project throughout.

The RACI Matrix would be as below.

| Activity / Decision Area | Mr. Henry (Sponsor) | Mr. Pandu (Financial Head) | Mr. Dooku (Project Coordinator) | Farmers (Peter, Kevin, Ben) | Manufacturers | APT IT (Mr. Karthik – Delivery Head) | Mr. Vandanam (Project Manager) | Developers / Testers | BA (You) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Approval & Funding | Accountable | Consulted | Consulted | Informed | Informed | Consulted | Informed | Informed | Informed |
| Budget Decisions | Consulted | Accountable | Consulted | Informed | Informed | Informed | Informed | Informed | Informed |
| Project Planning & Timeline | Informed | Consulted | Consulted | Informed | Informed | Accountable | Responsible | Informed | Consulted |
| Requirement Gathering | Informed | Informed | Consulted | Consulted | Consulted | Informed | Informed | Informed | Responsible |
| Requirement Validation | Informed | Informed | Consulted | Consulted | Consulted | Informed | Informed | Informed | Responsible |
| Design & Development | Informed | Informed | Informed | Informed | Informed | Consulted | Accountable | Responsible | Consulted |
| Testing | Informed | Informed | Informed | Informed | Informed | Informed | Consulted | Responsible | Consulted |
| UAT (User Acceptance Testing) | Informed | Informed | Informed | Responsible | Consulted | Informed | Consulted | Responsible | Consulted |
| Deployment | Accountable | Consulted | Consulted | Informed | Informed | Consulted | Responsible | Informed | Informed |

#### Question 7: Help Mr. Karthik to prepare a business case document

Answer:

Business Case Document:

Title – Online Agriculture Product Store (Web & Mobile Application)

Prepared by – Mr. Karthik, Delivery Head at APT IT Solutions

Abstract:

Farmers in remote areas face a lot of challenge in procuring Pesticides, seeds and fertilizers. These are very essential Agricultural products. These farmers further had to be relying on suppliers and other vendors like middlemen for all of these products. Because of which they also had to face a lot of challenges like giving high costs, limited availability goods and alternative solutions, and invest a lot of time in travelling and then waiting for the delivery of the goods.

This project aims at developing an Online Agriculture Product store (Web & Mobile Application) that will connect the farmers directly to the manufactures. This aims at providing transparent pricing, more accessibility and home delivery of the products.

The budget allocated for the project is 2 Crores and the project needs to be submitted in 18 months

Executive Summary: Why is this project initiated?

  - The farmers in the remote areas are struggling to access essential agricultural products like seeds, fertilizers and pesticides.

  - Existing supply chains are inefficient, costly and time consuming

  - Mr. Henry wants to create a digital solution to empower farmers and improve their productivity.

  - The project will connect farmers directly with manufacturers, making the process transparent, affordable, and reliable.

Business Objectives

- Provide farmers easy access to agricultural products through digital platforms.

- Eliminate middlemen and ensure fair pricing.

- Improve farmer productivity by ensuring timely availability of quality inputs.

- Enhance rural digital adoption in line with Digital India initiatives.

Current Challenges: (What are the current problems? – AS IS Situation)

- Farmers travel long distances to buy products.

- Dependence on middlemen which used to lead to higher costs, lack of transparency.

- Product unavailability during peak farming season.

- Lack of product knowledge and trusted information.

- Limited payment options (mostly cash).

- No tracking of product delivery.

Proposed Solution: (With this project, how many problems could be solved? - TO-BE Situation)

- A user-friendly web & mobile application where farmers can:

- Browse/search fertilizers, seeds, and pesticides.

- Place orders directly from manufacturers.

- Pay securely using multiple options (UPI, wallet, COD).

- Receive doorstep delivery.

- Track their orders and get notifications.

- Manufacturers can list products directly and reach rural customers. This will enhance and ensure better product availability

- Eliminates middlemen which will lead to fair & transparent pricing.

- Provides doorstep delivery which will further save time and travel costs. It will also enable order tracking and status notifications.

Resources Required:

- Human Resources: BA, Project Manager, Developers, Testers, DB & Network Admin, Trainers.

- Technology Resources: Servers/cloud storage, website & mobile app, database, secure payment gateway.

- Financial Resources: ₹2 Crores budget

- Logistics Resources: Delivery partners for remote areas.

How much organizational change is required to adopt this technology?

There would not be much changes required to adopt the technology. For Farmers, they would need to start using smartphones and its features more widely just to get the hands on experience of the app and website. On the manufacturers side, they would require to list the products on the website.

Risk Analysis

Adoption Risk: Farmers may resist digital platforms

Connectivity Issues: Poor internet in villages

Requirement Changes: Farmers may request new features

Delivery Challenges: Logistics in remote areas

Benefits / Value Creation for the stakeholders

For Farmers

- Easy access to quality products.

- Reduced costs by eliminating middlemen.

- Time savings with doorstep delivery.

- Better decision-making with product info.

For Manufacturers

- Direct access to rural markets.

- Increased sales & reduced distribution costs.

For APT IT Solutions

- Market leaders by taking first step into something like AgriTech domain.

- Future business opportunities.

#### Question 8: The Committee of Mr. Henry, Mr. Pandu, and Mr. Dooku and Mr. Karthik are having a discussion on Project Development Approach. Mr. Karthik explained to Mr. Henry about SDLC. And four methodologies like Sequential, Iterative, Evolutionary and Agile. Please share your thoughts and clarity on Methodologies

Answer:

1. Sequential (Waterfall Model)

The sequential model is a step-by-step approach where each phase must be finished before the next begins.
For example, first requirements are gathered, then design, then coding, then testing, and finally delivery.
It is easy to understand and manage since everything is planned from the start.
The budget and timelines are more predictable.
However, it is very rigid, meaning changes cannot be easily made later.
If farmers realize they want a new feature after development, it becomes costly.
This model works best when requirements are fixed and will not change.
For our agriculture store, this may not be the best fit.

2. Iterative Model

The iterative model develops the system in small versions, also called iterations.
Each version has a few features, which are improved in the next cycle based on feedback.
This way, farmers and manufacturers can see early results instead of waiting for the full system.
It allows corrections and improvements during the project.
The project becomes more flexible than Sequential.
However, it requires careful planning to manage multiple versions.
Users might sometimes find frequent changes confusing.
Still, it is helpful when requirements are not clear from the beginning.

3. Evolutionary Model

The evolutionary model starts with a simple, basic version of the system.
Over time, new features are added, and the system evolves step by step.
For example, first the app may only show products, then later include payments and delivery tracking.
This gives farmers an early usable system.
It reduces risks because the project grows in manageable stages.
It requires active involvement from stakeholders to guide new features.
The final system may take longer to become fully complete.
This model is practical for projects like ours, where needs change gradually.

4. Agile Model

The agile model works in short cycles called sprints, usually 2–4 weeks.
In each sprint, the team delivers small but usable features.
Farmers can quickly try these features and give feedback.
The system continuously improves with user involvement.
It is very flexible and adapts well to changing needs.
However, it requires close coordination and active participation from stakeholders.
Planning is less rigid compared to other models.
Agile is highly suitable for our project since farmers’ needs may change often.

While the Sequential model offers stability, it may not suit this project because farmers’ needs are not fully defined and may change as they use the system. Both Iterative and Evolutionary models allow gradual improvement and are safer choices. However, Agile would give the maximum flexibility and fastest value to farmers, making it the most suitable approach for building the Online Agriculture Store.

#### Question 9: They discussed models in SDLC like waterfall RUP Spiral and Scrum. You put forth your understanding on these models.

When the APT IT SOLUTIONS company got the project to make this online agriculture product store, there is a difference of opinion between a couple of SMEs and the project team regarding which methodology would be more suitable for this project. SMEs are stressing on using the V model and the project team is leaning more onto the side of waterfall model. As a business analyst, which methodology do you think would be better for this project?

Answer:

  - Waterfall Model

The Waterfall model is the oldest and most traditional SDLC model.
It follows a step-by-step process: 1. Requirements  2. Design 3. Development 4. Testing 5. Deployment.
Each stage must be completed before the next one starts.
It is simple, structured, and easy to manage for projects with fixed needs.
The cost and timeline are predictable because everything is planned upfront.
But, it is very rigid — changes are difficult once the project moves forward.
If requirements are unclear or may change, this model struggles.
It works best for projects where requirements are stable and well-understood.

  - Rational Unified Process (RUP)

RUP is a framework developed by IBM that combines iterative and disciplined processes.
It divides the project into four phases: Inception, Elaboration, Construction, and Transition.
Each phase has defined goals like understanding requirements, designing, developing, and delivering.
It allows flexibility by building the system in iterations while still keeping structure.
Stakeholders can see progress at different stages and give feedback.
However, RUP can be complex and requires skilled resources to manage properly.
It is useful for medium to large projects with evolving requirements.
Compared to Waterfall, it balances structure and flexibility.

  - Spiral Model

The Spiral model focuses strongly on risk management.
The project is developed in cycles (spirals), with each cycle including planning, risk analysis, development, and evaluation.
It is especially helpful for large, complex, and high-risk projects.
By evaluating risks at every stage, problems can be addressed early.
It combines the structured approach of Waterfall with the flexibility of Iterative models.
However, it can be expensive and time-consuming due to repeated risk assessments.
It requires expert project managers to implement successfully.
Spiral is best for projects where risks are high and requirements may change often.

  - Scrum (Agile Methodology)

Scrum is a popular Agile framework that works in short cycles called sprints (2–4 weeks).
The project team delivers small usable features at the end of each sprint.
Roles are clearly defined: Product Owner (manages requirements), Scrum Master (facilitates process), and Development Team.
Daily short meetings (Daily Stand-ups) ensure quick updates and issue resolution.
It focuses on teamwork, flexibility, and continuous customer involvement.
Changes can be easily managed as the project moves forward.
It delivers value to users quickly and continuously.
Scrum is highly suitable for projects like our agriculture store, where requirements may evolve.

Waterfall is very structured and easy to manage but rigid. It works well when requirements are fixed and clear from the beginning. RUP provides a balance by combining structure with iterations. It is good for medium to large projects where requirements may evolve gradually. Spiral is best suited for high-risk and complex projects. It focuses on risk analysis at every stage but can be costly and time-consuming. Scrum (Agile) is the most flexible and user-friendly. It delivers value quickly, adapts to changes easily, and requires strong teamwork and stakeholder involvement.

However, the point to discuss is between the V Model, and Waterfall Model to choose in between for the -The V-Model and the Waterfall Model are quite similar, but the main difference is the importance given to testing.

- In Waterfall, the project flows step by step — requirements, design, development, testing, deployment. Testing mainly happens after development is complete.

- In the V-Model, every development stage has a corresponding testing stage. For example, requirements have acceptance testing, design has system testing, and coding has unit testing. This ensures that quality is checked at every stage, not just at the end.

Now, for the Online Agriculture Product Store:

- Farmers are new to technology, and requirements may not be very detailed or perfectly clear in the beginning.

- If we only use Waterfall, we may discover issues too late, during final testing. That could delay the project and increase costs.

- With the V-Model, we get more assurance of quality and correctness at each stage. It reduces risks of rework and ensures the system is truly usable by farmers.

In the waterfall model, a clear structure and defined phases would be required. Since the project is to be submitted in 18 months of time, a strict time frame and set of development needs to be followed. The challenge with Waterfall model is that it would not be adaptive. And the requirements in the latter stage would not be encouraged.

On the other hand, V model involves testing of the development along with other phases in continuation during the Software development process. The early testing would help in identifying defects at an early stage which will reduce the rework required in latter stages of development. It is more suitable for projects with some level of uncertainty in requirements, allowing for adjustments based on testing feedback. It is more complex than waterfall model because of the Testing phase involved as a parallel activity in the process.

To choose a methodology, I would consider the potential of changes in requirement. Also, would want to understand that how much involvement would be of the users.

My recommendation for the project is to consider V Model. It will have evolving requirements from the farmers since not everything is defined. Also, the defect identification in early stage will help reducing the time. User involvement in V Model will also help refine and make the project efficient.

#### Question 10: Write down the differences between waterfall model and V model.

Answer:

Waterfall Model

- The process flows step by step, just like water flowing down a waterfall.

- First, requirements are gathered, then design is made, then coding is done, after that testing happens, and finally deployment.

- Testing happens only after the whole development is completed.

- If any mistake is found, it will be discovered very late (during testing).

- It is rigid – once one step is finished, it is hard to go back and make changes.

- If requirements were misunderstood at the start, the whole project can suffer.

- This model works better when requirements are clear and fixed from the beginning.

V-Model

- Every development step has a matching testing step.

- Testing is not left to the end – it is planned along with every stage.

- For example: when requirements are written, acceptance tests are also planned. When design is done, system tests are also prepared, and so on.

- Mistakes or gaps can be caught earlier since testing is connected to each stage.

- It is also structured and rigid, but less risky than Waterfall because testing is done in parallel.

- Costs are lower compared to Waterfall, because errors are identified earlier, saving time and rework.

- This model works well in projects where quality and correctness are very important.

#### Question 11: As a BA, state your reason for choosing one model for this project

Answer:

For the Online Agriculture Product Store project, I would choose the V-Model over the Waterfall Model.

Reasons:

- Farmers are new to using online applications, so the system must be simple, correct, and error-free. The V-Model checks quality at every stage.

- If requirements are misunderstood (for example, how farmers will place an order), the V-Model helps us identify this early through corresponding tests, instead of waiting until the end.

- Fixing mistakes in Waterfall is costly because they are found late. In V-Model, problems are caught earlier, saving time and money.

- Since Mr. Henry and the farmers are investing their trust in this system, continuous validation at each stage builds confidence that the product will meet their needs.

- Like Waterfall, it is structured, but V-Model gives an extra safety net with parallel testing

For this project, where user-friendliness and trust are critical, the V-Model is the better choice. It ensures the system works well for farmers, reduces risks, and increases the chances of delivering a successful product within the given time and budget. For the Online Agriculture Product Store, the V-Model methodology is more suitable than the Waterfall model. This is because the V-Model integrates testing at every stage of development, ensuring that errors and gaps are detected early. In a project where farmers, many of whom may be first-time technology users, depend on reliability and ease of use, quality becomes the highest priority. The V-Model reduces risks, avoids costly rework, and provides stakeholders with confidence that requirements are being validated continuously. Hence, it is the most effective approach to ensure a robust, error-free, and user-friendly system within the given budget and timeframe.

#### Question 12: The Committee of Mr. Henry, Mr. Pandu, and Mr. Dooku discussed with Mr. Karthik and finalized on the V Model approach (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) Mr. Vandanam is mapped as a PM to this project. He studies this Project and Prepares a Gantt chart with V Model (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) as development process and the Resources are PM, BA, Java Developers, testers, DB Admin, NW Admin.

Answer:

Below is the Gantt Chart for the project. The phases planned are RG – Requirement Gathering, RA – Requirement Analysis, Design, D1 – Development Module 1, T1 – Testing Module 1, D2 – Development Module 2, T2 – Testing Module 2, D3 – Development Module 3, T3 – Testing Module 3, D4 – Development Module 4, T4 – Testing Module 4, UAT – User Acceptance Testing.

Agile Gantt chart - Capstone 1.xlsx

Gantt Chart – Development wise

|  | 2025 |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb |
| RG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Gantt Chart – Resources

|  | 2025 |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb |
| PM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Developers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DB Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NW Admin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Testers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Farmers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#### Question 13: Explain the difference between Fixed Bid and Billing projects

Answer:

|  | Fixed Bid Project | Billing (Time & Material) Project |
| --- | --- | --- |
| Scope | Clearly defined and fixed upfront | Flexible, can change as project progresses |
| Budget | Fixed price agreed at the start | Variable, depends on actual effort and time |
| Timeline | Fixed timeline decided before project begins | Flexible, depends on evolving requirements |
| Risk | Vendor bears the risk of extra effort/costs | Client bears the risk of increasing costs |
| Flexibility | Low – difficult to handle changes later | High – can easily accommodate new changes |
| Best suited for | Projects with stable, well-defined requirements | Projects with evolving or unclear requirements |
| Example | Simple online store with fixed features | Research-based or evolving product development |

#### Question 14: Prepare Timesheets of a BA in various stages of SDLC. 1. Design Timesheet of a BA 2. Development Timesheet of a BA. 3. Testing Timesheet of a BA 4. UAT Timesheet of a BA. 5. Deployment n Implementation Timesheet of a BA

Answer:

| Sr no. | Stage | Detailed BA Activities | % Effort | Hours / Week (40 hrs) |
| --- | --- | --- | --- | --- |
| 1 | Requirements Gathering (RG) | - Meet with farmers, manufacturers, and committee members to understand needs - Conduct workshops and interviews to gather requirements - Document business requirements in BRD - Share drafts and incorporate feedback - Finalize and obtain stakeholder sign-offs | 25% | 10 hrs. |
| 2 | Requirements Analysis (RA) | - Break down high-level requirements into detailed use cases and process flows - Develop Requirement Traceability Matrix (RTM) - Validate requirements with SMEs for accuracy and completeness - Support feasibility study with technical and financial teams | 20% | 8 hrs |
| 3 | Design | - Review system design documents to ensure business requirements are addressed - Provide clarifications on workflows, data inputs/outputs, and business rules - Ensure usability and simplicity for farmers - Update RTM to check design coverage | 15% | 6 hrs |
| 4 | Development & Testing (D1–T4) | - Clarify requirements for developers during coding - Participate in daily/weekly stand-ups to resolve requirement gaps - Review test cases prepared by testers to ensure alignment with requirements | 15% | 6 hrs |
| 5 | User Acceptance Testing (UAT) | - Prepare UAT test scenarios/scripts based on requirements - Coordinate with farmers/stakeholders for UAT execution - Log and track UAT defects/issues in RTM - Facilitate communication between business users and project team | 15% | 6 hrs |
| 6 | Deployment & Implementation | - Supporting Go-Live readiness (checklists, data) - Coordinating with Dev, Test, Ops teams - Preparing training materials for end-users - Conduct user training sessions (farmers & company reps) - Document lessons learned for future improvements | 10% | 4 hrs |

Below is the elaborative timesheet for the BA in every SDLC Phase

1. Design Stage – BA Timesheet

| Activity | % of Time | Hours (per week, assume 40 hrs) |
| --- | --- | --- |
| Reviewing and finalizing requirements | 25% | 10 hrs |
| Creating process flows / wireframes | 25% | 10 hrs |
| Supporting design discussions with Dev | 20% | 8 hrs |
| Preparing requirement traceability matrix | 15% | 6 hrs |
| Stakeholder meetings / clarifications | 15% | 6 hrs |

2. Development Stage – BA Timesheet

| Activity | % of Time | Hours (per week) |
| --- | --- | --- |
| Clarifying requirements to developers | 30% | 12 hrs |
| Attending daily standups / project calls | 20% | 8 hrs |
| Updating RTM (Requirement Traceability) | 20% | 8 hrs |
| Handling change requests from stakeholders | 20% | 8 hrs |
| Documentation updates / sign-offs | 10% | 4 hrs |

3. Testing Stage – BA Timesheet

| Activity | % of Time | Hours (per week) |
| --- | --- | --- |
| Reviewing test cases | 25% | 10 hrs |
| Supporting testers with requirement queries | 25% | 10 hrs |
| Performing requirement validation testing | 20% | 8 hrs |
| Updating requirement-doc/test traceability | 20% | 8 hrs |
| Defect meetings / clarifications | 10% | 4 hrs |

4. UAT Stage – BA Timesheet

| Activity | % of Time | Hours (per week) |
| --- | --- | --- |
| Preparing UAT scenarios with business users | 25% | 10 hrs |
| Coordinating with users/farmers for execution | 25% | 10 hrs |
| Logging and tracking UAT issues | 20% | 8 hrs |
| Providing clarifications on requirements | 20% | 8 hrs |
| Ensuring sign-off from stakeholders | 10% | 4 hrs |

5. Deployment & Implementation Stage – BA Timesheet

| Activity | % of Time | Hours (per week) |
| --- | --- | --- |
| Supporting Go-Live readiness (checklists, data) | 25% | 10 hrs |
| Coordinating with Devlopment, Test, Ops teams | 25% | 10 hrs |
| Preparing training materials for end-users | 20% | 8 hrs |
| Conducting user training / knowledge transfer | 20% | 8 hrs |
| Post-deployment support (issue clarifications) | 10% | 4 hrs |