## Slide 1: COTRACK
Prepared By
Swati Rai
Date
13/01/2025

## Slide 2: Cotrack Insurance Policy Management Software
The Cotrack project is a centralized software platform designed to streamline homeowner insurance policy management.
It consolidates all essential policy details, such as holder, company, agent, premium, and principal information, and includes a built-in calling system for addressing missing data. Developed using the Waterfall methodology, Cotrack ensures a structured, predictable process with defined phases.
The project targets a June 2025 launch, promising enhanced efficiency, reduced errors, and improved user satisfaction while addressing potential risks through proactive planning.

## Slide 3: Situation/Problem/Opportunity
Requirement Misunderstanding: Misinterpreting client
requirements could lead to rework and delays.
Scope Creep: Clients may request additional features after
requirements are finalized, disrupting the timeline.
Data Accuracy Issues: Incomplete or inaccurate insurance data
might hinder the system's functionality.
Testing Bottlenecks: Insufficient time or resources for thorough
testing could lead to undetected bugs.

## Slide 4
Integration Challenges: Combining different system components and ensuring compatibility might be complex.
Resource Constraints: Limited availability of skilled developers, testers, or designers could delay progress.
Resistance to Adoption: Analysts and users might be reluctant to switch to the new system.
Timeline Pressure: Strict deadlines could lead to rushed phases, affecting quality.

## Slide 5
OPPORTUNITIES
Process Optimization: Streamlining policy management could highlight inefficiencies in existing workflows.
Data Insights: Consolidated data could provide valuable insights for insurers and agents.
User Training: Training sessions for the software can improve user skills and satisfaction.
Market Differentiation: Successfully deploying Cotrack could position the company as a leader in insurance technology.
Future Scalability: Building a robust foundation could make future upgrades or feature additions easier.

## Slide 6: Purpose Statement (Goal)
Build Cotrack, a software solution designed to centralize homeowner insurance policy management. This system will:
Provide comprehensive access to policyholder, insurance company, and agent details.
Include a built-in calling system to address missing details and streamline communication.
Enhance operational efficiency and reduce errors in data handling.

## Slide 7: Project Objectives
Centralized Data Management: Create a unified platform for storing and accessing homeowner policy details.
Detailed Information Coverage: Ensure the software captures and displays:
  Policy Holder’s Information: Name, address, contact details.
  Insurance Company’s Information: Name, contact, claims support.
  Agency/Agent’s Information: Name, license number, contact.
  Premium and Deductible Details: Amounts, due dates, and terms.
  Principal Amount Information: Coverage and policy limits.

## Slide 8
3.Integrated Communication: Incorporate a calling system to:
  Allow analysts to contact clients directly for missing details.
  Log call summaries and outcomes for future reference.
  4.Waterfall Methodology: Use a structured approach for development with clearly defined phases.

## Slide 9: Success Criteria
Key Indicators of Success:
Deployment: Cotrack launched successfully by June 2025.
Performance: Policy details retrieved within 5 seconds or less.
Impact: A 50% reduction in missing details cases within 3 months.
User Feedback: Positive reviews from at least 90% of pilot users.
Adoption: 100% usage by analysts for policy management and communication.

## Slide 10: Methods/Approaches
Development Approach: Waterfall Methodology
Requirement Gathering (January 2025): Collect and finalize all client requirements.
Design (February 2025): Develop system architecture, database schema, and UI/UX designs.
Implementation (March-April 2025): Code the solution, integrate features, and ensure functionality.
Testing (May 2025): Perform end-to-end testing to identify and resolve bugs.

## Slide 11
Deployment (June 2025): Launch the software and provide training to users.
Why Waterfall?
Sequential phases ensure clarity and focus.
Thorough documentation minimizes ambiguity.
Testing phase catches errors before deployment.
Defined timelines improve predictability and accountability.

## Slide 12: Resources
Project Manager: Manages timelines, budgets, and overall
project execution.
Software Developers: Build and code the software's front-end
and back-end functionalities.
QA Testers: Validate the software by testing for bugs,
usability, and performance issues.
Business Analysts: Translate client needs into technical
requirements for the team.
UI/UX Designers: Create user-friendly and visually
appealing software interfaces.

## Slide 13
Technical Resources:
Cloud Infrastructure: Centralized data storage for policy details.
Development Tools: Software like Visual Studio, SQL Server, and programming languages.
Calling System Integration: Tools for VOIP or similar systems.
Testing Tools: Platforms like Selenium for automated testing.
Financial Resources:
Budget: $500,000 allocated for development, testing, deployment, and post-launch support.

## Slide 14: Risks and Dependencies
Risks:
Scope Creep: Unclear or changing requirements can delay the project.
Client Feedback Delays: Lack of timely responses from stakeholders.
Integration Issues: Challenges in linking the calling system with the main platform.
Training Adoption: Analysts may require additional time to adapt to the new system.

## Slide 15
Dependencies:
Timely approval of requirements and designs.
Availability of skilled technical resources.
Reliable telecommunication systems for the calling feature.
Access to complete and accurate policy data from clients.

## Slide 16: Key Features of Cotrack
Policy Holder’s Information:
  Name, address, and contact details.
  Policy history and updates.
Insurance Company’s Information:
  Company name and contact details.
  Claims support and escalation points.
Agency/Agent’s Information:
  Agent’s name, license number, and contact details.
  Assigned regions or policy areas.

## Slide 17
Premium and Deductible Details:
  Amounts due, deadlines, and penalty terms.
Principal Amount:
  Coverage, policy limits, and exclusions.
Calling System:
  Direct calling functionality for analysts.
  Ability to log and store call summaries in the system.

## Slide 18: Timeline and Milestones
January 2025: Requirement gathering and finalization.
February 2025: System design and architecture.
March-April 2025: Development phase with coding and feature integration.
May 2025: Testing, debugging, and final refinements.
June 2025: Deployment and user training.

## Slide 19
Key Milestones:
Completion of requirement gathering by January 31, 2025.
Design phase approval by February 28, 2025.
Development phase completion by April 30, 2025.
Testing and QA completion by May 31, 2025

## Slide 20: Final Stage
Finalize Requirements: Ensure all client needs are documented and approved.
Initiate Design Phase: Begin system design by February 2025.
Regular Reviews: Conduct bi-weekly progress updates with stakeholders.
Pilot Testing: Test the system with a selected group of users in May 2025.
Post-Deployment Support: Provide continuous support for analysts post-launch.

## Slide 21
Thank You