## Slide 1: Project Progress Tracking Feature in Sparsh Application
Prepared by: Sarath Guru Raj A.V.R Date : 15.02.2025

## Slide 2: Situation/Problem/Opportunity
Problem Statement
Sparsh Application lacks a dedicated project progress tracking feature.
Current manual processes are time-consuming and error-prone.
Current Challenges
Limited visibility into project milestones and tasks affects project management quality
Delays in obtaining real time project updates create communication gaps
Inconsistent data reporting reduces decision-making accuracy.
Identified Opportunities
Introduce a real-time tracking feature to enhance project management and aligns with organization's digital transformation goals.
Improve collaboration and eﬃciency across teams which boost overall productivity.
Reducing dependency on manual methods will minimize errors.
Enhanced visibility will empower managers with actionable insights.

## Slide 3: Purpose Statement (Goals)
Goal Overview
To Design and implement a Project Progress feature that provides real-time updates on task completion and milestones and align the project with organizational objectives for digital transformation to enhance user experience with intuitive and user-friendly interfaces.
Importance of this project
Improves decision-making with accurate, real-time data.
Improve project management through real-time updates and notifications
Ensure seamless integration with existing app features.
Support strategic decision-making with performance dashboards.
Ensure robust security and data protection mechanisms
Supports better collaboration across departments.

## Slide 4: Project Objectives
Short Term Objectives
Develop a fully functional Project Progress module within six months.
Train users for smooth adoption of the new feature.
Integrate milestone-based notifications for timely alerts.
Enhance collaboration and customizable project reports for different stakeholders.
Conduct regular performance reviews post-implementation.
Long Term Objectives
Achieve 90% user adoption within one year.
Reduce manual project tracking efforts by 50% and project management errors by 20%.
Maintain continuous feedback and support channels.
Ensure compatibility with existing modules in Sparsh App.

## Slide 5: Success Criteria
Here are the main acceptance criteria for the project progress tracking feature,
Project Reports & Analytics : Dynamic reports with visual charts and export options like PDF, Excel.
Performance & Speed: Dashboard loads within 2 seconds and reports are generate in 5 seconds.
User Friendly Interface: Easy navigation, drag and drop functionality and tooltips for guidance.
Milestone &Task Management: Users can view live project status updates with milestone completion.
Automated Notifications & Alerts: Alerts for milestones completions, overdue tasks and project delays
Stakeholder approval & Business Impact : 90% of UAT approval, 80% of user adoption within 3 months, and 50% reduction in manual tracking.
.

## Slide 6: METHODS
Here we use the WATERFALL METHODOLOGY,
So,
Waterfall methodology is a linear and sequential process in which each phase depends on the deliverables of the previous one.
Five key phases: Requirement gathering and analysis, Design, Development, Testing, Deployment.
Suitable for projects with clear requirements and limited changes and also offers well-documented stages for better control.
Ensures comprehensive testing before deployment and reduces ambiguity through detailed documentation.

## Slide 7: Approach
Requirement Gathering & Analysis:
Identify key stakeholder needs and feature requirements.
Document and validate all requirements.
Design:
Create detailed workfiows and user interface designs.
Ensure compatibility with existing app modules.
Development:
Build and integrate the module into Sparsh App.
Conduct unit testing during development.
Testing:
Conduct functional, performance, and security testing to validate the feature
Identify defects, resolve issues, and optimize system performance
UAT:
Deploy in a controlled environment and simulate project scenarios to meet requirements
Gather feedback from end-users and project managers.
Deployment:
Roll out the feature in the production environment with minimal downtime.
Provide comprehensive user training and support.
Maintenance:
Track system performance, fix bugs, and roll out updates as needed.
Implement improvements and ensure compliance with data security policies.

## Slide 8: Project Timeline (Gantt Chart)
Requirement Gathering & Analysis: 1 month
Design Phase : 1 - 2 months
Development Phase : 1 - 2 months
Testing and Deployment : 1 month

## Slide 9: Resources Allocation
People Resources
Project manager (1) , developers (4) , testers (2) , business analysts (1).
External consultants for specialized support like SME’s, delivery Head if required.
Technical Resources
Development tools, testing software, and project management tools.
Budget & Time Resources
Development and training costs, licensing fees, and contingency budget.
Budget : ₹ [90 Lakhs].
Six months for development, testing, and deployment.

## Slide 10: Risks and Dependencies
Risks | Mitigation
1. Technical - Integration issues with existing Sparsh App modules. System downtime or performance lag due to new feature implementation. | Perform thorough testing (UAT, performance, security)
2. Operational - Lack of proper training leading to ineffective usage. Poor user interface design affecting user engagement. | Conduct training workshops and ensure user feedback sessions.
3. Financial - Budget overruns due to additional software development costs. Underestimation of training and support expenses. | Have a contingency budget (10-15% buffer).
4.Project Management - Delays in development due to resource unavailability. Scope creep if new feature requests arise mid-development. | Use project management tools (JIRA, Asana) for real-time tracking.
Dependencies
Internal Dependencies: IT team availability, stakeholder approvals, internal training programs.
External Dependencies: Third-party API integrations, licensing approvals, software updates.

## Slide 11: Expected Deliverables &Benefits
Business Benefits
Improved project tracking and visibility.
Enhanced collaboration and accountability.
Real-time Project Progress Dashboard.
Milestone-based notifications and alerts
Operational Benefits
Reduction in manual tracking efforts.
Better decision-making with visual dashboards
Comprehensive training materials for all users.
Support documentation and FAQs

## Slide 12: Conclusion and Next Steps
Summary
The Project Progress feature will improve Sparsh App functionality.
Supports better decision-making through real-time data.
We recommend proceeding with resource allocation and implementation.
Waterfall methodology ensures a well-structured and reliable approach.
Next Steps
Approval of project plan.
Resource allocation and kick-off meeting.

## Slide 13: THANK YOU
Project Sponsor: ABC Enterprises, LTD
Project Manager: Ram Kumar