## Slide 1: Project Title: Enhancing the Genesis Application with Agile Methodologies Subtitle (optional): A Live Agile Project at Tata AIG Prepared By: Vidyashree Date: 8th June 2025

## Slide 2: Executive Summary
Project Overview:
This live Agile project focuses on enhancing the Genesis system used at Tata AIG. The goal is to empower local operations teams to directly process renewal endorsements and cashier activities within the application.
Problem:
Currently, certain tasks are dependent on central teams, leading to delays and reduced efficiency. Local operations lack direct access, causing bottlenecks and slower service delivery.
Importance of Solving the Issue:
By enabling local operations to handle tasks independently, we can save time, reduce dependency, and deliver faster, more efficient service to customers.
How Agile Helps:
Using Agile methodology allows us to implement iterative enhancements, gather continuous feedback, and make quick, incremental improvements to the Genesis system.
Vision of Success:
A smoother workflow where local teams operate independently, leading to quicker turnaround times and improved customer satisfaction.

## Slide 3: Purpose Statement / Goals
Purpose :
The purpose of this project is to enhance the Genesis application by enabling local operations teams to independently process renewal endorsements and cashier activities. This will reduce dependency on centralized teams, improve turnaround time, and ensure faster, more efficient service delivery to customers.
Goals of the Project:
Decentralize endorsement and cashier activities
Minimize workflow delays and dependency bottlenecks
Improve operational efficiency across branches
Enhance customer experience with quicker resolutions
Align Genesis with Agile principles for faster delivery and flexibility

## Slide 4: Project Objectives
Identify and gather requirements for enhancement of Genesis to support local operations functionalities
Develop and integrate modules in Genesis that allow local teams to process:
Renewal endorsements
Cashier activities
Implement Agile practices like sprint planning, user stories, backlog management, and continuous feedback during development
Conduct UAT (User Acceptance Testing) with selected users from local operations teams
Train users and support staff for smooth transition and adoption of the new features
Ensure successful Go-Live with minimal disruption to ongoing operations

## Slide 5: Success Criteria
Project Success Will Be Measured By:
Enablement of Local Ops Teams
Local teams successfully performing renewal endorsements and cashier activities independently within the Genesis system.
Improved Turnaround Time
At least 30% reduction in processing time for endorsement and cashier-related requests within 2 months of deployment.
Increased System Usage
80% of local operations users actively using the new modules within the first month post-implementation.
User Satisfaction
Minimum of 90% positive feedback from local operations teams during UAT and after rollout.
System Stability
New modules should maintain 99% uptime and function without critical bugs for 3 consecutive sprints.

## Slide 6: Methods / Approach
Requirement Gathering & Analysis
Form a cross-functional team including local ops reps, IT team, and BAs
Identify key user stories and acceptance criteria for enhancements
Sprint Planning & Development
Break down features into smaller tasks and prioritize them into 2-week sprints
Develop modules for renewal endorsement and cashier access
Continuous Feedback & Iteration
Conduct sprint reviews and retrospectives
Incorporate stakeholder and user feedback in each cycle
UAT & Training
Involve local ops users for testing
Conduct structured training sessions and provide documentation
Go-Live & Support
Final implementation in the live Genesis system
Provide post-go-live support and monitor adoption metrics

## Slide 7: Required Resources
People
Project Manager
Business Analyst (you)
Genesis Development Team
QA/Testers
Local Operations Representatives
Agile Coach (if available)
Time
Estimated Project Duration: 4 Months
2 weeks: Requirements & Planning
6 weeks: Development
3 weeks: Testing & UAT
3 weeks: Deployment & Support

## Slide 8: Required Resources
Budget (Assumed / Sample)
Software customization & development – ₹XX,000
UAT & Training materials – ₹XX,000
External tools/consultants (if any) – ₹XX,000
Total Estimated Budget: Not to exceed ₹000000.00
Tools & Other Resources
Agile tracking tools (e.g., Jira or Excel-based board)
Training documentation & demo environments
System access for UAT testers
Reporting tools like Dataquest (if applicable

## Slide 9: Risks & Dependencies
Risks
User Resistance to Change
Some local operations staff may be reluctant to adopt the new system due to comfort with existing manual processes.
Technical Integration Challenges
Integrating new modules into the existing Genesis platform may lead to compatibility or performance issues.
Training Gaps
Insufficient training may lead to incorrect usage or underutilization of new features.
Downtime During Rollout
There may be minor disruptions during go-live which could impact ongoing operations temporarily.

## Slide 10: Risks & Dependencies
Dependencies
Timely Inputs from Local Ops Teams
Success depends on active collaboration and feedback from end users during development and testing.
Support from IT & Dev Teams
Availability of internal technical teams is essential for timely development and deployment.
Management Approval & Budget Clearance
Stakeholder buy-in and budget approval must happen on schedule to avoid delays.

## Slide 11: To Be Completed by Appropriate Manager
Project Sponsor …………………………………………………….
Project Manager ………………………………………………………

## Slide 12: THANK YOU