Waterfall Live Project 1- Part 1 / 2

Document 1:

- Why is this project initiated?

The project has started because the existing CRM at ICICI Bank is mainly for reporting and does not support daily work. RMs waste time on manual tasks, BMs lack real-time performance views, and customer insights are missing. By adding AI, mobile access, and dashboards, the new CRM aims to save time, increase sales, and improve customer experience.

- What are the current problems?

The current CRM has major gaps: RMs waste time on manual entry, it is not integrated with other banking apps, lacks smart insights for customer engagement, and BMs cannot track real-time performance—making interactions more transactional than relationship-driven.

- With this project, how many problems could be solved?

- RMs save time by avoiding repeated data entry.

- All customer/sales/service data in one system.

- AI gives alerts for cross-sell, upsell, and churn risk.

- BMs get instant dashboards on branch/team performance.

- Bankers can approach customers with personalized offers, not just react.

- What are the resources required?

- Project Manager- to manage the complete project and monitor progress.

- Business Analyst- to gather requirements and bridge between business and technical teams.

- Developers- to make changes and enhancements in the CRM application.

- Testing Team- to test the system and ensure quality.

- How much organizational change is required to adopt this technology?

The organizational change required is moderate. Bankers (RMs/BMs) will need to adopt new ways of working with CRM, such as using mobile CRM, relying on AI insights, and reducing manual work. This will mainly need training, habit change, and management support. The bank’s overall structure will not change, only the way employees use CRM in daily tasks.

- Time- frame to recover ROI?

The time- frame to recover ROI for this CRM enhancement project is expected to be around 18–24 months. This is because benefits like improved sales conversion, higher cross-sell, faster service resolution, and better customer satisfaction will gradually increase revenue and efficiency after full adoption.

- How to identify Stakeholders?

We use RACI Matrix to identify stakeholders and their role in the project:

- Responsible (R):  Person who does the work (Business Analyst gathers requirements).

- Accountable (A): Decision maker of the work Project Manager ensures delivery).

- Consulted (C): who gives input/advice Compliance team for rules).

- Informed (I): Gets updates (Senior Management).

Document-2

- Business Process Model

Goals: 
To enhance CRM so that it provides AI insights, mobile access, dashboards, and compliance checks.

Inputs: 
Customer details like CRN, Mobile No, PAN No, and transaction history.

Resources: 
RMs, BMs, IT team, CRM vendor, and support staff who use and manage the system.

Activity: 
Bankers get a single 360° customer view, track leads, suggest products, and resolve service requests faster.

Value Added Service: 
Better customer experience, improved sales conversion, higher productivity, and employee satisfaction.

- SWOT

Strength: 
Bank already has a CRM system in place, so staff is familiar with basic usage.

Weakness:
Current CRM is used mostly for reporting, not for daily productivity or customer engagement.

Opportunity: 
By adding AI insights and mobile CRM, bank can improve sales and customer satisfaction.

Threat: 
Employees may resist using the new system if they are not trained properly

- Strength – Strong Market Recognition

- Weakness – Staff Awareness for the Application is low

- Opportunity – Expansion in Market

- Threat- very poor competitor.

  - Feasibility Study

Means checking whether the project is possible to execute or not with available resources, technology, budget, and time.

- Resources :- CRM Application (CRMNEXT), Bank Staff, and IT Support

- Hardware :- Secure Servers, Strong Network Connectivity

- Software :- CRMNEXT Application with AI & Dashboard features

- Team :- Business Analyst, Developers, Testers, Project Manager, Vendor Team

- Budget :- Estimated Budget is ₹1.5 Crore (approx.)

- Time :- Project completion timeline is 8–9 Months

Gantt Chart

| Resources | Week 1-5 | Week 6-15 | Week 16-25 | Week 26-35 | Week 36-45 | Week 46-52 |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager |  |  |  |  |  |  |
| Business Analysist |  |  |  |  |  |  |
| Java/CRM developers |  |  |  |  |  |  |
| Data Science Team |  |  |  |  |  |  |
| Tester |  |  |  |  |  |  |
| Network Engineer |  |  |  |  |  |  |
| CRM Vendor |  |  |  |  |  |  |

- GAP Analysis

Gap Analysis means comparing the current state (AS-IS) with the desired future state (TO-BE) to find out what is missing and what needs to be improved.

- AS-IS (Current State):
Presently, the CRM system (CRMNEXT) is used mainly as a reporting tool. Security features are weak, customer interaction history is not fully visible, and personalized offers for each customer are not displayed.

- TO-BE (Future State):
The enhanced CRM will have stronger security features, complete customer interaction history (360° view), and display personalized offers and insights. This will help bankers engage better with customers and improve sales.

  - Risk Analysis

BA Risk: Incomplete requirements, lack of domain knowledge, wrong market understanding.

Process Risk: Complicated steps for users, incomplete product details, inefficiency in workflows.

Project Risk: Scope creep, budget overrun, delay in timeline, vendor dependency.

User Adoption Risk: RMs/BMs may resist using new CRM → solved by training & gamification.

Data Quality Risk: Wrong/missing data may reduce AI insights.

Elicitation Techniques we used to complete a Project

- Document Analysis :-   A mandatory technique used in almost every project. I am applying it to understand the current state of the application by reviewing emails, meeting minutes, and existing documents to identify enhancements.

- Reverse Engineering :-  This technique is important for migration or enhancements. I am using it to analyze the existing system and build an improved version of the application.

- Focus Groups :-   Involve people with similar domain knowledge so they can share ideas and suggest improvements together.

- JAD Session :-  Since the project is technical in nature, the technical team’s role is crucial for its success.

- Documents to Write for the Project

- BRD (Business Requirement Document): Explains business needs and objectives.

- FSD (Functional Specification Document): Explains how the system should function.

- FRD (Functional Requirement Document): Details specific functional requirements in depth.

- Use Case Document: Shows step-by-step interactions between user and system.

- What process to follow to sign off on the Document?

Sign-off will be taken on the SRS document, as it is the key document that captures all requirements. The client can provide sign-off through an official email approval or a signed copy of the document.

- How to take Approvals from the Client?

First, arrange a meeting with the client to share updates and take their feedback. After that, send a formal email with the final document, and once the client confirms, it is considered approved (sign-off).

- What Communication Channels to Establish and Implement?

The communication can be done through email updates, regular face-to-face meetings, telephonic discussion and messaging platforms like- Teams/ WhatsApp.

- How to handle a change request?

First, the request is received formally through a Change Request Form. Once received, the team acknowledges it and analyses its impact on the project in terms of time, cost, and scope. After the analysis, the change  request is either approved or rejected based on discussions with the client and the project team to ensure smooth implementation without affecting overall project delivery.

- How to update progress of the project to the stakeholders?

Project progress can be shared through weekly status emails and monthly review meetings. These updates keep stakeholders informed about milestones achieved, challenges faced, and next steps of the project.

- How to take sign-off on UAT – Client Project Acceptance Form?

For our project, we will first prepare the UAT form and conduct testing with users. Any issues will be reviewed and fixed. Then the Client Project Acceptance form will be prepared and formal approval obtained. Finally, the signed form will be documented and shared with all stakeholders.

Document-3

Functional Specifications

| Project Name | Enhancement in CRM NEXT OF ICICI Bank |
| --- | --- |
| Customer Name | ICICI Bank |
| Project Version | Version 1.0 |
| Project Sponsor | Customer Experience (CX) Department or Retail Banking Business Team |
| Project Manager | ANJALI SINHA |
| Project Initiation Date | 20.08.2025 |

Functional Requirement Specifications

| Req. ID | Req. Name | Description | Priority |
| --- | --- | --- | --- |
| FR0001 | Login | Secure login with SSO, MFA, biometrics; role-based access; works on desktop & mobile; session timeout and encryption. | 1 |
| FR0002 | Display | Single customer view with products, balances, KYC flags, interactions, RM notes, tickets, and sentiment in one screen. | 2 |
| FR0003 | Search | Smart search by CRN/Mobile/PAN/Name; shows results across systems; supports fuzzy match, nearby customers, and de-duplication.. | 3 |
| FR0004 | Result | Results page will show AI suggestions, churn alerts, reminders (KYC/renewals), and one-click actions (leads, meetings, SRs) with SLA timers. | 4 |
| FR0005 | Offers | AI-based personalized offers, cross-sell/upsell, easy consent, one-tap fulfilment, and automatic tracking for dashboards. | 5 |

Document-4

Requirement Traceability Matrix

| Req. ID | Req. Name | Req. Description | Design | D1 | T1 | D2 | T2 | UAT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR0001 | Login | User must be able to securely login | Completed | Completed | Completed | Completed | Completed | Completed |
| FR0002 | Search | System must search customer details by CRN, Mobile no., PAN with correct results. | Completed | Completed | Completed | Completed | Completed | Completed |
| FR0003 | Display | Once CRN entered, system should show 360° customer profile with all interactions. | Completed | Completed | Completed | Completed | Completed | Completed |
| FR0004 | Result | System should provide AI-driven insights, next best opportunity. | Completed | Completed | Completed | Completed | Completed | Completed |
| FR0005 | Offers | System should display pre-approved offers for the customer. | Completed | Completed | Completed | Completed | Completed | Completed |

Document-5

RACI CHART

| TASK | Project Sponsor | Project Manager | Business Analyst | Developers/Testers | Client(RM/BM) |
| --- | --- | --- | --- | --- | --- |
| Req. Gathering | A | R | R/A | C | C |
| System Design | C | A | R | C | C |
| Implementation( Development/integration) | C | A | C | R | C |
| Testing & quality verification | C | A | C | R/A | C |
| UAT & Client review | C | A | R | C | R/A |
| Maintenance & Updates | C | A | C | R | C |
| Final approval & Handover | A | R | C | C | C |

- R = Responsible (does the task)

- A = Accountable (final decision/ownership)

- C = Consulted (provides input)

- I = Informed (kept updated)

Introduction

Business Goal: Improve ICICI Bank’s CRM to give RMs and BMs smarter insights, simpler processes, and better customer engagement tools — boosting sales, branch productivity, and customer loyalty.

Business Objective

- Reduce manual work b to free bankers’ time for customers.

- Provide 360° customer view with product recommendations.

- Enable real-time dashboards for Branch Managers.

- Cut service request time for faster resolutions.

- Boost customer satisfaction (NPS) in one year.

Business Rules

- Only authorized users can log in securely

- Customer details fetched only with valid CRN.

- Personalized offers shown only if eligible.

Background

ICICI Bank’s CRM helps with customer details, leads, service requests, and reports, but it’s mainly used as a reporting tool rather than a daily working tool.

Project Objectives

- Cut down manual work by 30% so they can spend more time with customers.

- Give bankers a full 360° view of each customer, plus smart predictions on what products to offer           next.

- Provide real-time dashboards so BMs can instantly track branch and team performance.

- Reduce service request handling time by 40%, so customers get quicker resolutions.

- Improve customer satisfaction (NPS) by 15% within one year.

Project scope: In scope

- AI-driven insights suggest next best products and track customer sentiment.

- Unified RM workbench gives one screen for all sales and service tasks.

- Mobile CRM enables geo-tagging, offline updates, and nearby customer view.

- Real-time dashboards help BMs track performance and productivity.

- Automated compliance checks and lifecycle alerts ensure timely actions.

Out of scope

- Core banking system changes are not included.

- ATM, net banking, and UPI systems are out of scope.

- Third-party app integrations beyond CRM are excluded.

- Hardware upgrades or new infrastructure setup not covered.

- Employee HR/training systems are outside the project scope

Assumptions

- RMs & BMs will access CRM via desktop/mobile.

- Stable internet for dashboards & sync.

- Users will be trained.

- Timely approvals & budget.

- Accurate customer data.

Constraints

These are the following constraints of the project:

- Budget – Limited funding allocated for CRM upgrade.

- Time – Project must be delivered within fixed timeline.

- Compliance – Must strictly follow RBI & ICICI policies.

- Integration – Dependent on existing core banking systems.

- Data Quality – CRM performance relies on clean, accurate data.

Risks

- User Adoption – RMs/BMs may resist; solved via training & gamification.

- Data Quality – Wrong/missing data makes AI insights unreliable.

- Integration – CRM must connect well with core systems & apps.

- Compliance – Must strictly follow RBI & ICICI policies.

### AS-IS (Current State)

- Multiple disconnected systems

- No complete customer view

- Manual tracking and compliance

- Delayed reporting

### TO-BE (Future State with CRMNEXT)

- Unified platform with CRM Next

- Customer 360° view

- AI-driven insights

- Automated compliance

- Mobile CRM

- Real-time dashboards

AS-IS Process:

- Customer data scattered across systems → Manual updates → No 360° view → Compliance/reporting delays.

TO-BE Process:

- Unified CRMNEXT → 360° view → AI insights → Automated compliance → Mobile CRM → Real-time dashboards.

Business Requirement

| ID | Requirement | Priority | Notes |
| --- | --- | --- | --- |
| BR01 | AI-driven insights to suggest next best product & track sentiment | High | Helps RMs cross-sell/upsell and improve customer focus |
| BR02 | Unified RM Workbench (single screen for sales & service) | High | No need to switch multiple systems |
| BR03 | Mobile CRM with geo-tagging & offline mode | Medium | Supports field bankers to work on-the-go |
| BR04 | Branch Manager dashboards with real-time performance | High | Enables monitoring of branch KPIs and team productivity |
| BR05 | Automated compliance & lifecycle triggers (KYC, renewals) | High | Ensures RBI/ICICI policies are always followed |

### Appendices

- Acronyms

- CRM → Customer Relationship Management

- RM → Relationship Manager

- BM → Branch Manager

- KYC → Know Your Customer

- NPS → Net Promoter Score

- Glossary

  - Customer 360° View - a single unified profile showing all customer details, accounts, and interactions.

  - Geo-tagging - mapping customer locations to help bankers identify nearby clients.

  - Next Best Product - AI-based recommendation for the most suitable product to offer a customer.

  - Lifecycle Trigger - Automated alerts/events based on customer milestones (e.g., renewal, maturity).

- Related Documents

  - Business Requirement Document (BRD)

  - Functional Requirement Specification (FRS)

  - RACI Matrix

  - Test Plan & UAT Sign-off Forms

Introduction

The CRM NEXT project will give ICICI Bank RMs and BMs smarter tools with AI insights, a 360° customer view, and real-time dashboards. It reduces manual work, improves customer service, and boosts sales productivity.

Functional Requirement

| Req. ID | Description | Priority | Source |
| --- | --- | --- | --- |
| FR001 | Secure Login & Authentication for users to access CRM NEXT. | High | Business Sponsor / IT Security Policy |
| FR002 | Search customers using CRN, name, or account number. | High | Business Users (RMs/BMs) |
| FR003 | Display 360° customer view (details, transactions, interactions). | High | Customer Engagement Dept. |
| FR004 | AI-driven insights for next best product offers & customer sentiment. | Medium | Project Sponsor / Business Growth Team |
| FR005 | Real-time dashboards for RMs & BMs to track performance & issues. | High | Branch Managers / Operations |

Non- Functional Requirement

| Req. ID | Description | Priority | Source |
| --- | --- | --- | --- |
| NFR001 | System should respond within 2 seconds for customer searches. | High | End Users |
| NFR002 | 24/7 availability with 99.9% uptime. | High | IT Infrastructure Team |
| NFR003 | Must scale to handle thousands of concurrent users. | Medium | IT Team |
| NFR004 | Data security with RBI compliance & encryption standards. | High | Compliance Dept. |
| NFR005 | Mobile CRM with geo-tagging & offline sync support. | Medium | RMs / Sales Team |

Requirement Traceability Matrix

| Req. ID | Description | Type | Priority | Source | Notes |
| --- | --- | --- | --- | --- | --- |
| FR001 | Secure Login & Authentication for CRM NEXT. | Functional | High | IT Security / Business Sponsor | Enables controlled access to system. |
| FR002 | Search customers using CRN, name, or account number. | Functional | High | RMs/BMs | Core functionality for daily use. |
| FR003 | Display 360° customer view (details, transactions, interactions). | Functional | High | Customer Engagement Dept. | Supports customer insights. |
| FR004 | AI-driven insights for next best product & sentiment analysis. | Functional | Medium | Project Sponsor / Sales | Improves cross-sell/upsell. |
| FR005 | Real-time dashboards for RMs & BMs to track branch/team performance. | Functional | High | Branch Managers / Operations | Improves branch productivity. |
| NFR001 | System must respond within 2 seconds for searches. | Non-functional | High | End Users | Ensures smooth user experience. |
| NFR002 | 24/7 availability with 99.9% uptime. | Non-functional | High | IT Infrastructure | Required for banking operations. |
| NFR003 | Must handle thousands of concurrent users (scalability). | Non-functional | Medium | IT Team | Supports growth & load handling. |
| NFR004 | Data security with RBI compliance & encryption standards. | Non-functional | High | Compliance Dept. | Protects customer data. |
| NFR005 | Mobile CRM with geo-tagging & offline sync support. | Non-functional | Medium | Sales / RMs | Ensures mobility & flexibility. |

UAT

| UAT ID | Test Scenario | Test Steps | Expected Result | FR ref. |
| --- | --- | --- | --- | --- |
| UAT-01 | Secure Login | Enter valid/invalid credentials and log in | User is authenticated with valid details; error shown for invalid | FR001 |
| UAT-02 | Customer Search | Enter CRN and click search | System fetches and displays customer record instantly | FR002 |
| UAT-03 | Display Customer 360° View | Open customer profile | Full customer details, transactions, and interactions shown | FR003 |
| UAT-04 | AI-driven Insights | Select a customer with history | Next best product & sentiment suggestion displayed | FR004 |
| UAT-05 | Branch Dashboard | RM/BM logs into dashboard | Real-time view of branch performance and pending tasks visible | FR005 |

Project Assumption

| Assumption ID | Assumption Description |
| --- | --- |
| A-01 | A user should correctly enter valid customer details in the system. |
| A-02 | A user will provide complete details such as CRN, Mobile Number, PAN Number, etc. |
| A-03 | The system will automatically fetch and display details related to the entered customer. |
| A-04 | The user is assumed to have basic knowledge of online access (login, navigation, etc.). |
| A-05 | The user is assumed to have sufficient knowledge to use the CRM application effectively. |