## Slide 1: Core Customer Support Application
Prepared by: Renuka Date: 15-04-2025

## Slide 2: Situation/Problem/Opportunity
Currently, itunes store customer support is fragmented across multiple platforms, leading to delayed responses, lack of visibility, and inconsistent customer experiences. There is a need for a unified tool that combines chat and email and calling option in a single interface to ensure faster, more reliable support.

## Slide 3: Purpose Statement (Goals)
This proposal outlines the development of a core application for omnichannel customer support. The platform will empower support agents to engage with customers via chat, email, and voice calls. It will provide agents access to customer account information, suggest relevant help articles, and allow customers to submit feedback through surveys. This initiative aims to improve customer satisfaction, streamline agent workflows, and unify communication channels into a single interface.

## Slide 4: Project Objectives
Develop a centralized customer support tool with:
Real-time chat functionality
Email integration (send/receive)
Improve agent productivity and response time
Maintain a history of all customer interactions
Enable analytics and reporting on support performance
View and manage customer account details.
Access and share knowledge base articles
Capture customer feedback through surveys
Improve customer satisfaction and support team efficiency
Enable insightful reporting and data-driven decision making

## Slide 5: Success Criteria
Real-time chat and email integration work seamlessly
Unified dashboard for managing all customer interactions
Automatic ticket creation for all conversations
System handles 100+ concurrent chats without lag
< 2 sec chat delivery time, < 30 sec email sync time
95%+ test cases passed during UAT
No critical bugs at go-live
99.9% uptime post-launch
100% user adoption within 2 weeks of rollout
30%+ improvement in response time
50% reduction in missed/delayed tickets
Data encryption and secure storage in place
Positive user feedback on ease of use
Training & documentation completed pre-launch
Go-live sign-off from key stakeholders

## Slide 6: Methods and Approaches
Project Methodology: Waterfall model with clearly defined phases
Requirement Gathering: Stakeholder interviews, workshops, BRD documentation and User stories and Usecases.
Design Approach: Wireframes, prototypes, and user feedback loops
Technology Stack: React/Angular (frontend), Node.js/.NET (backend), PostgreSQL/MongoDB
Modular Development: Separate modules for chat, email, call, knowledge base, surveys
API Integrations: Twilio (calls), Gmail/Outlook API (emails), CMS/KB platform, survey tools
Testing Strategy: Unit, integration, system, and UAT with real users
Training & Onboarding: Manuals, live sessions, agent-focused materials
Deployment Plan: Staging → Pilot team → Full rollout
Post-Go-Live Support: Monitoring, feedback collection, iterative improvements

## Slide 7: Resources
Human Resources
Project Manager – Oversee planning, execution, and delivery
Business Analyst – Requirements gathering, documentation, and validation
UI/UX Designer – Wireframes, prototypes, and design assets
Frontend Developers – Build user interfaces (React/Angular)
Backend Developers – Develop APIs, integrate with third-party tools
QA/Test Engineers – Manual and automated testing
DevOps Engineer – CI/CD setup, staging & production environments
Support Team Leads – UAT, feedback, and training
Content Writer – Knowledge base articles and survey content

## Slide 8: Technical Resources
Development Tools – VS Code, GitHub, Postman, Swagger
Design Tools – Figma / Adobe XD
Project Management – Jira / Trello / MS Project
Communication APIs – Twilio (Call), Sendbird/CometChat (Chat), Gmail/Outlook API (Email)
Database – PostgreSQL / MongoDB
Hosting Environment – AWS / Azure / On-premises servers
Knowledge Base System – Zendesk Guide / Custom CMS
Survey Tools – Google Forms / Typeform / Built-in module

## Slide 9: Project Timeline
Phase | Duration | Deliverables
Requirements Gathering | 1 Week | Requirements Document (BRD)
UI/UX Design | 2 Weeks | Wireframes, Mockups
Development | 5 Weeks | Core Features
Testing & QA | 2 Weeks | Test Reports, Bug Fixes
UAT & Feedback | 1 Week | Final Adjustments
Deployment & Training | 1 Week | Live System, User Training

## Slide 10: Project Budget (Estimated)
Category | Estimated Cost (INR)
Human Resources | 
- Project Manager | ₹4,980
- Business Analyst | ₹4,150
- UI/UX Designer | ₹3,320
- Developers (FE & BE) | ₹1,660
- QA/Test Engineers | ₹4,150
- DevOps Engineer | ₹2,490
- Content Writer | ₹1,660
Software & Tools | 
- API Licenses (Twilio, Chat, Email) | ₹2,490
- Hosting (AWS/Azure) | ₹2,075
- Design & Dev Tools | ₹8,300
Training & Onboarding | ₹1,245
Contingency (10%) | ₹4,980
Total Estimated Budget | ₹39,010

## Slide 11: Risks and Dependencies
Key Risks
API Integration Delays – Third-party service latency or changes
Data Privacy Issues – Risk of non-compliance with data regulations
Scope Creep – Uncontrolled feature additions can delay delivery
User Adoption Resistance – Support agents may resist new tools
Testing Bottlenecks – Delays in UAT feedback or QA cycles
Downtime or Failures – Unstable cloud or telephony services

## Slide 12: Key Dependencies
Chat, Email, Call APIs – e.g., Twilio, Gmail API, Sendbird
Customer Account Database – Access and permissions required
Knowledge Base Platform – Existing CMS or articles
Survey Tool Integration – Google Forms, Typeform, or custom
Legal/Compliance Approvals – Required for data handling and support policies
Training Team Availability – For onboarding and agent enablement

## Slide 13: To be completed by Appropriate Manager
Name | Role | Signature | Date
XYZ | Project Sponsor | - | -
ABC | Project Manager | - | -