## Slide 1: Structured Growth of Flipkart Sub-Furniture Category using Waterfall Model
Prepared By – Tarang Ovhal
Date – 18th April 2025

## Slide 2
Situation:
In the period leading up to the COVID-19 pandemic (2019–2020), the online furniture market in India was entering a high-growth phase, with rising demand from Tier 2 and Tier 3 cities driven by increasing digital adoption, expanding internet penetration, and rising aspirations for affordable home improvement.
Flipkart was strategically focusing on expanding its Furniture category — particularly in functional and fast-moving verticals such as Metal, Plastic, Kids, and Outdoor Furniture. These sub-categories showed strong potential due to their value-driven appeal and logistics-friendly product dimensions.
However, despite strong customer demand, the category operations were facing structural challenges:
Lack of Standardized Onboarding: Vendor discovery and onboarding lacked a formal framework, leading to inconsistent performance and delayed launches.
Long SLAs: Delivery timelines for bulky items were as high as 14 days, reducing customer satisfaction and repeat purchases.
Fragmented Catalog Quality: Selection Design Scores (SDS) were low (~55%) due to gaps in listing content, pricing hygiene, and product visibility.
Operational Silos: Coordination between catalog, ads, vendor ops, and logistics teams was fragmented, affecting overall execution.
The organization recognized the need to transition from an ad hoc approach to a structured project model, where vendor expansion, catalog enhancement, SLA improvement, and marketing alignment could be managed in a phased, scalable way — setting the stage for this Waterfall-based category growth project.

## Slide 3
Problem:
As Flipkart aggressively expanded its Home & Furniture vertical, particularly in value-led segments like Metal, Plastic, Kids, and Outdoor Furniture, operational cracks began to surface that threatened scalability and customer satisfaction. The following core challenges were observed:
Inconsistent Vendor Capabilities: There was no structured framework to evaluate vendor readiness. Onboarding relied heavily on individual buyer relationships rather than data-backed assessments, leading to varied service levels across sellers.
Extended Delivery Timelines: The average SLA stood at 10+ days for bulky items, well above industry benchmarks. Causes included weak inter-warehouse planning, delayed dispatches, and poor last-mile logistics coordination, all of which eroded customer trust.
Low SDS (Selection Design Score): Catalog quality was sub-optimal with incomplete listings, unstructured attributes, poor imagery, and inconsistent pricing. As a result, the category suffered from poor visibility on platform filters and search, directly impacting conversions.
Lack of Operational SOPs: Vendor onboarding, SLA setting, ad planning, and catalog audits lacked formal SOPs.nternal teams worked in silos, with limited visibility into overall vendor health or category performance.
Ad Spend Misalignment: Without a unified plan, many sellers either under-invested in ads or overspent without ROI visibility.This directly impacted seller performance, budget utilization, and Flipkart’s overall profitability from the category.
These problems were not just tactical — they were systemic, and pointed to the urgent need for a structured, phased approach to category management. That’s where the Waterfall model was introduced: to define, implement, and scale repeatable processes that would help Flipkart build a high-growth, high-efficiency Furniture category

## Slide 4
Opportunity:
In the 2019–2020 phase, India’s online furniture market was at a pivotal stage. Reports from RedSeer, Bain & Co., and other industry sources indicated a rising demand for affordable, ready-to-ship, and space-efficient furniture products—especially from Tier 2 and Tier 3 cities.
Flipkart recognized a strategic growth opportunity in scaling the Metal, Plastic, Kids, and Outdoor Furniture verticals — categories that were underserved by premium furniture brands but highly relevant to a value-conscious customer base.
This opportunity was defined by several factors:
1. Category Leadership in a High-Demand Segment: While many organized players focused on premium wood and modular furniture, Flipkart had the chance to dominate the utility segment by offering quality, affordable products with faster delivery.
2. Scalable Vendor Ecosystem: India’s plastic and metal furniture manufacturing base is well-established, especially in states like Maharashtra, Punjab, and Tamil Nadu. By identifying and enabling these vendors, Flipkart could create a broad and reliable supply chain with minimal setup friction.
3. Growing Customer Expectations: Customers increasingly expected faster delivery, detailed listings, competitive pricing, and better variety. Improving SLA and SDS directly addressed these expectations and could drive higher conversion and retention.
4. Operationally Efficient Category: These segments inherently had lower return rates and fewer service issues compared to bulky or customized furniture. That made them ideal for process-based scale-up using structured project frameworks like the Waterfall model.
5. Strategic First-Mover Advantage: By investing early in streamlining operations, onboarding vendors, and improving catalog quality, Flipkart had the opportunity to set a benchmark in this segment — both in sales and operational excellence.

## Slide 5
Purpose Statement (Goals)
The primary goal of this project was to create a scalable and structured framework to grow Flipkart’s Furniture category with a focus on Metal, Kids, Outdoor, and Plastic segments. The intent was to drive consistent business growth while solving for operational inefficiencies.
Project Objectives
Identify potential vendors in Metal, Kids, Outdoor, and Plastic segments through structured data analysis.
Conduct feasibility checks based on delivery capability, fulfillment readiness, and product quality.
Onboard and train selected vendors on Flipkart’s operational and cataloging standards.
Reduce the average delivery SLA from 10 to 5 days by improving dispatch rates, inter-warehouse transfers, and last-mile delivery coordination.
Improve the Selection Design Score (SDS) from 55% to 80% by streamlining listing quality, pricing hygiene, and catalog depth.
Achieve consistent monthly ad spend utilization targets across all active vendors.
Deliver the annual operating plan (AOP) target of ₹150 Cr with a 22% month-on-month growth trajectory.

## Slide 6
Project Objectives:
The core objective of the project was to design and implement a structured, scalable model to drive growth in Flipkart’s Furniture category — particularly in the high-volume verticals of Metal, Plastic, Kids, and Outdoor Furniture.
The project was guided by clearly defined design criteria: operational efficiency, faster time-to-market, vendor scalability, improved catalog quality, and consistent customer experience. Each stage of the project aligned with these objectives:
1. Solution Selection Based on Defined Requirements: dentified critical process gaps across vendor onboarding, SLA adherence, catalog quality, and ad performance. Evaluated multiple operational models (centralized onboarding, category-specific SOPs, SLA triggers, automated reporting) and selected solutions aligned with Flipkart’s platform constraints, logistics capabilities, and vendor maturity. Ensured selected approaches were scalable across all four furniture sub-categories and matched Flipkart’s internal tooling and governance systems.
2. Solution Prototyping and Testing: Piloted onboarding SOPs and SLA monitoring tools with a small set of pre-vetted vendors in the Metal and Plastic verticals. Created a structured training module and monitored adoption of cataloging standards (images, attributes, pricing benchmarks). iterated on delivery improvement initiatives — dispatch process streamlining, inter-warehouse transfers, and last-mile coordination — using defined performance metrics (e.g., SLA%, SDS, ad spend ROI).
3. Operationalizing Success Metrics: Finalized success criteria including: SLA reduction to 5 days, SDS improvement to 80%, vendor onboarding TAT < 7 days, and monthly ad spend compliance. Built dashboards to track category health on a weekly basis, with clear ownership across internal teams.
4. Cross-Functional Alignment and Scalability: Engaged key stakeholders from Vendor Management, Catalog, Ads, and Logistics to ensure feasibility and accountability. Designed documentation and review cadences to enable continuous improvement post-implementation.
This structured approach ensured that every solution introduced was measurable, testable, and scalable — driving predictable outcomes aligned with business goals and Flipkart’s broader category management strategy.

## Slide 7
Success Criteria:
The project’s success was evaluated through a combination of performance metrics tied to Flipkart’s internal KRAs and measurable improvements in category health, vendor experience, and customer satisfaction. Each criterion was designed to reflect both the execution quality of the solution and the business value delivered.
1. SDS Uplift (Cataloging & RPD KRAs): Improved Selection Design Score from 55% to 80%+ across all four furniture verticals. Achieved through consistent catalog audits, standardization of product titles, enriched attributes, and richer product descriptions (RPD). Improved product discoverability and conversions in platform search and filters.
2. SLA Optimization (Stock & Demand Planning KRAs): Reduced delivery SLA from 10 to 5 days through optimized inventory placement, faster dispatch cycles, and tighter inter-warehouse coordination. Realigned supply plans based on zone-wise demand patterns to avoid overstocking and delays.
3. Vendor Onboarding Efficiency (Training & Enablement): Reduced vendor onboarding TAT (Turnaround Time) by over 30% using SOPs, automated checklists, and structured training sessions. Vendors met SLA and catalog hygiene benchmarks faster, ensuring better go-live compliance.
4. Discounting & Affordability Levers (Pricing, NCEMI KRAs): Launched event-linked discount strategies (especially for BBD) that maintained margins while driving scale. Implemented No-Cost EMI on high-ticket furniture items — boosting both AOV (Average Order Value) and conversion in Tier 2/3 audiences.
5. Stakeholder Satisfaction & System Maturity: Created shared dashboards for SLA, SDS, and ad spends — improving internal alignment and execution transparency. Positive stakeholder feedback across Category, Vendor Ops, Ads, and Catalog teams due to predictable, trackable performance cycles.
This results framework ensured that project success was not only defined by top-line growth — but by sustainable improvements in process reliability, tool adoption, vendor productivity, and customer experience — all directly mapped to your Flipkart KRAs.

## Slide 8
Methods / Approach:
The execution approach followed the classical Waterfall model, with clear phase-wise milestones across requirement gathering, solution selection, implementation, and go-live — customized for Flipkart's operational workflows and category needs. The step-by-step method followed:
1. Define Requirements & Evaluation Framework: Engaged with category leadership and internal stakeholders (Vendor Ops, Logistics, Catalog, and Ads) to define functional goals — SLA reduction, SDS improvement, and onboarding efficiency. Developed a structured requirement document that included success benchmarks, system readiness criteria, and expected vendor capabilities.
2. Vendor Identification and Feasibility Evaluation: Conducted a pan-India data scan using internal dashboards and market insights to shortlist sellers in Metal, Kids, Outdoor, and Plastic furniture categories. Used a feasibility scoring matrix to evaluate vendors on parameters like lead time, fulfillment readiness, catalog quality, and historical Flipkart performance.
3. SOP Design and Selection Committee Involvement: Formed a cross-functional selection committee consisting of Category Managers, Vendor Ops Leads, Catalog Specialists, and Planning Analysts. Designed operational SOPs including: onboarding workflow, SLA definition, catalog validation, and issue escalation paths.
4. Pilot Implementation & Internal Training: Selected a set of pilot vendors to test the full process — onboarding to ad optimization — across the Metal and Plastic categories.Trained internal teams on new documentation flows, SLA dashboards, and SDS audit tools to ensure smooth adoption of the system.
5. Solution Roll-Out and Support Setup: Post successful pilot KPIs, the solution was scaled to the Kids and Outdoor categories. Established internal support channels via centralized documentation, shared dashboards, and weekly review cadences with stakeholders.
6. Go-Live with Tracking Infrastructure: Transitioned to full-scale implementation across all verticals with category-specific tracking sheets, daily SLA monitoring, and SDS reporting integrated into Flipkart’s Vendor Hub and other tools. Instituted a continuous improvement loop — monthly KPI reviews, vendor feedback sessions, and cross-functional reviews.
This systematic approach ensured not just execution, but cross-team buy-in, vendor readiness, and long-term sustainability, enabling Flipkart to establish a reliable, scalable, and data-driven model to grow its Furniture category.

## Slide 9
Resources:
The successful execution of this project required coordination across internal teams, budget for enablement activities, and access to systems and tools to track performance metrics. Resources were categorized as follows:
People: Category Management Team: Responsible for vendor evaluation, onboarding planning, and solution design. Vendor Operations & Catalog Teams: Executed onboarding workflows, catalog audits, and SOP adoption. Business Analysts & Data Teams: Supported dashboard creation, KPI definition, and reporting standardization. Cross-functional SMEs: Involved from Ads, Logistics, Finance, and Seller Support for alignment and feedback.
2. Time: Total implementation timeline: 12 weeks (Achieved the KPI’s in 6 months): 2 weeks: Requirement finalization & process mapping -- 3 weeks: Vendor selection and SOP design. -- 3 weeks: Pilot run and training rollout. -- 4 weeks: Full-scale category deployment and review.
3. Budget: Training and Enablement: Internally budget was allocated for vendor handbooks, onboarding modules, and team workshops. -- Tooling and Reporting Setup: Covered within internal Flipkart systems ( Avengers, Theia, Hermas, SUV, Vendor Hub, FDP) — no incremental licensing cost. --Dashboard & Process Automation Support: Internal BI resources leveraged, reducing external dependency
4. Other Dependencies: Internal Platform Integration: Reliance on Hermes and FDP for real-time SLA and SDS tracking. -- stakeholder Reviews: Weekly check-ins with project sponsors and leadership. -- Reference Data and Competitive Insights: Secondary research on SLA norms and product listing standards from online benchmarking sources (Amazon, Pepperfry, Urban Ladder)
This resource structure ensured the project remained cost-effective, cross-functionally aligned, and executable without major system overhauls — leveraging existing Flipkart tech infrastructure and internal SME bandwidth.

## Slide 10
Risks and Dependencies
Risks:
Resistance to Change by Existing Vendors: Many long-term vendors were used to Flipkart's earlier informal or less-structured onboarding and catalog processes. Transitioning them to a stricter SOP and SLA framework required change management, training, and regular follow-ups.
Intuitiveness of the Current (Legacy) System: Existing workflows (for vendor onboarding, cataloguing, and SLA tracking) were considered intuitive by teams due to their repetitive nature. Introducing structured documentation and milestone-based monitoring felt time-consuming initially, causing reluctance from both internal ops teams and vendor managers.
Justifying Cost and Effort for Operational Improvements: Improvements like better SDS, faster delivery, and cleaner catalogs lead to long-term gains (e.g., higher NPS, lower returns), but these are difficult to quantify immediately in terms of ROI. Management often focuses on sales/GMV numbers; hence, presenting efficiency-related wins required clear before-after benchmarking.
System Dependence on Multiple Tools: Execution depended on coordination across Hermes, FDP, Helium10, and Vendor Hub. These tools operate in silos, and their integrations were not always smooth — creating a dependency risk on platform stability.
Logistics & Fulfillment Coordination: SLA reduction from 10 to 5 days relied on multiple stakeholders — warehousing, dispatch centers, and courier partners. Any gap in inter-team coordination could delay implementation.
Dependencies: Cross-Functional Collaboration: Success was dependent on timely inputs and cooperation from Vendor Ops, Catalog, Ads, and Supply Chain teams.
Vendor Capability: The plan assumed vendors had scalable operations — any overestimation in feasibility would risk missed KPIs.
Data Integrity & Visibility: Accurate SLA/SDS/ad metrics were crucial — dependency on real-time dashboards and correct tagging in tools was essential.

## Slide 11
Project Completion Summary
The Flipkart Furniture Waterfall Project was successfully executed with measurable improvements across all targeted verticals — Metal, Plastic, Kids, and Outdoor Furniture. Through a structured, phase-wise rollout aligned with the Waterfall methodology, the project addressed core operational challenges such as long delivery SLAs, inconsistent vendor onboarding, and suboptimal catalog quality.
Key achievements include:
SLA reduction from 10 to 5 days, driven by dispatch planning, warehouse sync, and logistics coordination
SDS improvement from 55% to 80%, resulting from SOPs, listing quality audits, and catalog training
Onboarding 20+ vendors using a standardized framework and feasibility model
100% monthly ad spend target compliance across onboarded sellers
₹150 Cr AOP delivered, with a 22% MoM growth trajectory
Cross-functional alignment achieved via clear roles, shared dashboards, and weekly KPI reviews
The project also delivered non-revenue wins like:
Better documentation and accessibility of category processes
Improved dashboard visibility for all key metrics (SLA, SDS, ad spends)
Higher stakeholder satisfaction due to transparency, accountability, and predictability in category operations
This structured, outcome-oriented approach has created a repeatable framework that can be scaled to other categories, serving as a model for future transformation initiatives within Flipkart’s marketplace ecosystem.

## Slide 12: Thank you