## Slide 1: "Optimizing Inventory Management at Raymond UCO"
Prepared By
VIPIN MESHRAM
Date: 02/05/2025

## Slide 2: Situation Raymond, a leading textile and apparel brand, currently faces significant challenges in managing its vast inventory across multiple warehouses and retail outlets. Raymond is currently facing inefficiencies in its inventory management due to outdated systems and lack of real-time visibility. These issues have led to frequent stock imbalances, delayed order processing, and increased operational costs. With expanding operations and a diverse product range, the need for a robust and centralized inventory management system has become critical to ensure optimal stock levels, minimize waste, and improve overall supply chain efficiency.
Manual inventory tracking using spreadsheets/paper logs.
Frequent stock discrepancies (overstocking/stockouts).
Delays in order fulfillment due to inaccurate data.

## Slide 3: Problem Raymond lacks an integrated inventory management system capable of providing real-time data across its warehouses and retail outlets. This has led to frequent stock mismatches, overstocking of slow-moving items, understocking of high-demand products, and delays in replenishment. These challenges reduce customer satisfaction, increase operational costs, and hinder the company's ability to make data-driven decisions.
Overstocking of slow-moving items and stockouts of fast-moving products
Delays in inventory reconciliation and real-time stock visibility
Increased operational costs and inefficiencies in order fulfillment
Difficulty in forecasting demand accurately due to fragmented data

## Slide 4: Opportunity Implementing a centralized and intelligent inventory management system offers Raymond the opportunity to streamline stock operations, improve demand forecasting, and enhance supply chain visibility. This will enable better decision-making, reduce inventory holding costs, prevent stockouts and overstock situations, and ultimately improve customer satisfaction and operational efficiency across all business units. 1. Operational Efficiency Boost Automated tracking reduces manual errors by 30%+ Real-time stock visibility cuts audit time by 50% Faster order processing improves fulfillment speed 2. Cost Savings 20% lower carrying costs through optimized stock levels Reduced rush orders via demand forecasting Minimized dead stock through expiry alerts 3. Strategic Business Growth Scalable system supports warehouse expansion plans Data-driven decisions using advanced analytics Competitive edge through reliable order fulfillment 4. Enhanced Compliance & Reporting Automated audit trails for regulatory compliance Customizable reports for management reviews Seamless ERP integration improves data accuracy 5. Employee Productivity Gains Simplified workflows reduce training time Mobile access enables remote stock checks Reduced stress from manual reconciliation

## Slide 5: Goals
To implement a centralized inventory management system that integrates data across Raymond’s warehouses and retail stores.
To improve real-time visibility of stock levels and product movement.
To reduce inventory holding costs and minimize overstocking/understocking issues.
To enable accurate demand forecasting and efficient replenishment cycles.
To enhance operational efficiency and decision-making through data-driven insights.

## Slide 6: Project Objectives
Select and implement an inventory management solution that aligns with Raymond’s operational, technical, and scalability requirements.
Design and prototype the solution to ensure usability, integration feasibility, and user acceptance.
Automate inventory tracking and reporting to reduce manual errors and improve accuracy.
Integrate the system with existing ERP and POS platforms to ensure seamless data flow.
Train relevant stakeholders to ensure smooth adoption and long-term sustainability of the system.

## Slide 7: Success Criteria
Improve real-time availability and accessibility of inventory data across all Raymond locations.
Reduce order processing time and enhance responsiveness to stock movements.
Minimize stock discrepancies by at least 80% through automated tracking.
Achieve a 95% accuracy rate in demand forecasting within the first six months of implementation.
Reduce inventory holding costs by at least 15% within one year of system deployment.
Ensure system uptime of 99% with minimal downtime or disruptions to operations.

## Slide 8: Resources Required
1. Human Resources
Core Team:
  Project Manager (1) - Oversees end-to-end execution
  IT Specialists (2) - System integration & troubleshooting
  Warehouse Supervisors (3) - Process alignment & ground-level feedback
  Finance Analyst (1) - Budget tracking
Support Roles:
  Vendor Consultants - Configuration & go-live support
  Trainers - Staff upskilling (internal or vendor-provided)

## Slide 9: Methods / Approach
Phase 1: Requirements Gathering & Committee Formation
Objective: Define business needs, technical specifications, and success metrics. Activities: ✔ Cross-Functional Committee:
Supply Chain (process owners)
IT (integration & security)
Retail Operations (end-user needs)
Finance (ROI & budget alignment) ✔ Document Requirements:
Must-haves (ERP integration, barcode/RFID support)
Nice-to-haves (AI demand forecasting, mobile access)
Constraints (budget, timeline, legacy system compatibility) Deliverable: System Requirements Document (SRD)

## Slide 10
Phase 2: Market Research & Vendor Selection (RFP Process)
Objective: Identify and evaluate potential solutions. Activities: ✔ Market Research:
Benchmark tools (SAP, Oracle, Zoho, Fishbowl)
Analyze case studies from similar industries ✔ RFP Process:
Send RFPs to shortlisted vendors
Evaluate based on:
  Functionality (real-time tracking, reporting)
  Scalability (multi-location support)
  Integration (ERP, POS, eCommerce)
  Cost (licensing, implementation, training) Deliverable: Vendor Shortlist & Scoring Matrix

## Slide 11
Phase 3: Vendor Demos & Final Selection
Objective: Validate vendor claims and select the best-fit solution. Activities: ✔ Live Demonstrations:
Test core features (barcode scanning, stock alerts)
Assess UI/UX for warehouse staff ease of use ✔ Reference Checks:
Contact existing clients for feedback
Verify post-implementation support quality Deliverable: Final Vendor Selection Report

## Slide 12
Phase 4: System Prototyping & Pilot Testing
Objective: Validate the solution in a controlled environment before full rollout. Activities: ✔ Configure System:
Customize workflows to match Raymond’s processes
Integrate with existing ERP ✔ Pilot Testing (1 Warehouse, 3 Months):
Measure accuracy gains (target: 30% error reduction)
Assess user adoption challenges
Fine-tune based on feedback Deliverable: Pilot Test Report & Go/No-Go Decision

## Slide 13
Phase 5: Training & Change Management
Objective: Ensure smooth transition for end-users. Activities: ✔ Role-Based Training:
Warehouse staff (barcode scanning, stock adjustments)
Managers (reporting, dashboards)
IT (troubleshooting, maintenance) ✔ Support Materials:
User manuals, quick-reference guides
FAQ repository for common issues Deliverable: Training Completion Certificates & Feedback

## Slide 14
Phase 6: Full-Scale Implementation
Objective: Roll out the system across all warehouses. Activities: ✔ Phased Deployment:
Warehouse 1 → Warehouse 2 → Warehouse N
Monitor system stability at each stage ✔ Data Migration:
Historical inventory data cleanup
Ensure no loss of critical records Deliverable: System Go-Live & Post-Implementation Review

## Slide 15
Phase 7: Post-Implementation Review & Optimization
Objective: Measure success and refine processes. Activities: ✔ Performance Review:
Compare KPIs (accuracy, fulfillment time, cost savings)
Identify improvement areas ✔ Continuous Support:
Helpdesk for issue resolution
Quarterly system audits Deliverable: Post-Implementation Optimization Plan

## Slide 16: Resources
1. Team
Core: 1 PM, 2 IT specialists, 2 supply chain analysts, 3 warehouse supervisors, 1 finance controller
Support: Vendor consultants (2 months), trainers (3 weeks)
2. Timeline (7 Months)
Planning (1.5 months)
Vendor Selection (1.5 months)
Pilot (2 months)
Rollout (2 months)
3. Budget (₹27.05 Lakhs)
One-Time: ₹21.5L (software, hardware, implementation)
Annual: ₹5.05L (hosting, maintenance, training)
Contingency: ₹2.7L (10% buffer)
4. Key Tools
ERP integration middleware
Testing sandbox environment
Barcode/RFID hardware

## Slide 17: Risks and Dependencies
1. User Resistance to New System
Risk: Employees may resist change due to familiarity with the old system.
Mitigation:
  Conduct hands-on training with real-life scenarios.
  Identify and train super-users to support peers.
  Implement a reward system for early adopters.
2. Difficulty Quantifying ROI
Risk: Management may question investment due to intangible benefits.
Mitigation:
  Track measurable KPIs (e.g., 30% faster audits, 20% fewer stockouts).
  Compare with industry benchmarks (e.g., average inventory accuracy).
  Highlight cost of inaction (current losses from errors and delays).

## Slide 18
3. ERP Integration Failures
Risk: Technical issues may disrupt operations.
Mitigation:
  Test integration in a sandbox environment first.
  Roll out phase-wise (one warehouse at a time).
  Include penalty clauses in vendor contracts for delays.
4. Data Migration Errors
Risk: Incorrect data transfer could cause inventory mismatches.
Mitigation:
  Run parallel systems (old + new) for 1 month.
  Use automated validation tools to check data accuracy.
  Assign a dedicated data cleanup team.

## Slide 19
5. Budget Overruns
Risk: Unplanned expenses may exceed allocated funds.
Mitigation:
  Allocate a 10% contingency buffer.
  Prioritize must-have vs. nice-to-have features.
  Monitor spending weekly with finance team.