## Slide 1: Implementation of an Enhanced Recruitment Tracking System - NextGreek
Prepared By: Vishnu UT Date:28-Feb-2025

## Slide 2: Situation:
The recruitment team currently relies on NextGreek for sourcing, activity tracking, candidate search and filtering, interview scheduling, personalized communication, pipeline management, performance measurement, and client-wise categorization.
There is an increasing need for an optimized system to streamline these processes and enhance efficiency.

## Slide 3: Problem:
The existing workflow experiences inefficiencies in candidate sourcing and filtering.
Activity tracking lacks real-time insights, affecting timely decision-making.
Interview scheduling challenges lead to delays in candidate engagement.
Measuring recruiter performance and managing client-wise pipelines is time-consuming.
Communication with candidates and stakeholders needs further personalization and automation.

## Slide 4: Opportunity:
Enhance NextGreek’s capabilities or integrate an advanced tracking system to optimize sourcing and filtering.
Implement AI-based recommendations to improve candidate matching.
Automate interview scheduling and candidate communication for better engagement.
Improve team performance tracking with real-time analytics.
Strengthen client-wise candidate categorization for more effective talent management.

## Slide 5: Purpose Statement (Goals):
Primary Goal:
To improve the recruitment tracking system by enhancing sourcing, filtering, activity tracking, and performance measurement, ensuring a streamlined and automated process.

## Slide 6: Project Objectives:
Optimized Sourcing & Filtering
Implement AI-driven recommendations to find the best candidates faster.
Advanced Activity Tracking & Reporting
Introduce real-time dashboards for monitoring recruiter activities.
Seamless Interview Scheduling
Provide automated calendar invites and reminders for interviewers and candidates.

## Slide 7
Personalized Communication
Automate bulk messaging with personalized templates for candidates.
Improve engagement through SMS, emails, and chatbot integration.
Client-Wise Categorization & Pipeline Management
Develop a structured system to manage candidates based on client-specific requirements.
Improve tracking of candidate movement within each pipeline.

## Slide 8: Success Criteria:
Reduction in sourcing time by 30 percent.
At least 50 percent reduction in scheduling conflicts.
Real-time visibility into recruiter key performance indicators.
Better candidate-client matching efficiency.

## Slide 9: Methods:
The project follows a Waterfall methodology, where each phase is completed before moving to the next, ensuring a structured and sequential approach.
Phase 1: Requirement Gathering (Week 1 - 2)
Identify inefficiencies in the current system (NextGreek).
Conduct stakeholder interviews with recruiters and hiring managers.
Define automation and analytics requirements.

## Slide 10
Phase 2: System Design (Week 3 - 4)
Finalize system architecture for AI-driven sourcing, scheduling, and analytics.
Define data flow for real-time recruiter performance tracking.
Phase 3: Development (Week 5 - 8)
Implement automation features for sourcing, filtering, and scheduling.
Develop recruiter dashboards for activity tracking.
Integrate enhanced candidate pipeline management.

## Slide 11
Phase 4: Testing & Quality Assurance (Week 9 - 10)
Conduct system testing to validate automation workflows.
Perform user acceptance testing (UAT) with recruiters.
Fix bugs and optimize system performance.
Phase 5: Deployment & Implementation (Week 11 - 12)
Go-live with the upgraded system.
Conduct training sessions for recruiters on new features.
Ensure post-launch support and feedback collection.

## Slide 12
Phase 6: Maintenance & Support (Ongoing)
Monitor system performance and address any issues.
Provide continuous updates and optimizations based on recruiter feedback.
Ensure compliance with data security regulations.

## Slide 13: Resources:
People:
IT Team (for development and system integration)
Recruitment Team (for system feedback and user training).
Time:
Total Implementation Timeline: 12 Weeks (3 Months).

## Slide 14
Budget:
Expected software and training costs: Rs. XXXXX
Other Resources:
AI-driven automation tools for sourcing and filtering.
Third-party software for scheduling and communication.

## Slide 15: Risks:
Resistance to New System Adoption
Recruiters may take time to adjust to automation.
Mitigation: Conduct hands-on training and provide a knowledge base.
Integration Challenges with NextGreek
Possible technical issues while enhancing automation.
Mitigation: Conduct early compatibility testing.

## Slide 16
Security and Compliance Concerns
Candidate data privacy needs to be safeguarded.
Mitigation: Implement GDPR-compliant security protocols.

## Slide 17: Dependencies:
Stakeholder cooperation for requirement gathering.
IT Team availability for system enhancement.

## Slide 18: Approval & Sign-Off:
Project Sponsor: Project Manager: