Document 1: Definition of Done

Project Name: Global TIS

Prepared By: Roopshree S.

Date: 07-07-2025

Definition of Done is a technique where the team agrees on, and prominently displays, a list of criteria which must be met before a backlog item is considered done.

Purpose of DoD:

The Definition of Done (DoD) ensures that every user story, task or increment delivered meets a shared standard of completeness and is ready for release or deployment. It reduces ambiguity and improves quality by providing clear, agreed-upon criteria.

General DoD Criteria:

| Area | Criteria |
| --- | --- |
| Requirements | The story is fully understood and accepted by Product Owner |
| Design | UI/UX is approved, and design complied with system standard. |
| Development | Code is written; peer reviewed and follows naming convention |
| Unit Testing | Unit test written and pass with 90%+ coverage |
| Integration | Code integration into the main branch without conflicts |
| Build/Deployment | Builds successfully in CI/CD environment. |
| Functional Testing | QA validates that feature works per acceptance criteria. |
| Non-Functional Testing | Performance, security and load testing completed. |
| Documentation | User story is documented. |
| PO Acceptance | Product Owner reviews and accepts the user story. |
| Regression Tested | Regression tests conducted and passed. |
| Demo-Ready | Feature is ready for sprint review. |
| Production-Ready | No critical bugs and can be released if required. |

Document 2- Product Vision

| Scrum Project: Global TIS |  |  |  |
| --- | --- | --- | --- |
| Venue: Virtual |  |  |  |
| Date: 08/07/2025 | Start Time: 10:00 AM | End Time: 6:00 PM | Duration: 8 hours |
| Client: Global TIS |  |  |  |
| Stakeholder: Webster Britney, Russ Micheal, Oliveria Joao, S Umesh |  |  |  |
| Scrum Team |  |  |  |
| Scrum Master: Vipul Sharma |  |  |  |
| Product Owner: Oliveria Joao |  |  |  |
| Scrum Developer 1: Divya Nayak |  |  |  |
| Scrum Developer 2: Neha Shinde |  |  |  |
| Scrum Developer 3: Saurabh D. |  |  |  |
| Scrum Developer 4: Kavita Bagle |  |  |  |
| Scrum Developer 5: Sunil More |  |  |  |
| Vision |  |  |  |
| Target - Bank and financial institution using Global TIS ATM network. - ATM operations teams, field service vendor and helpdesk engineer. - End-users/customers who reply on ATM services for transaction. | Need - Real-time monitoring of ATM performance and faults. - Reduce ATM downtime and improve response time to issues. - Provide secure, compliant and always available ATM access. | Product - A centralized ATM lifecycle management system. - Enables installation tracking, maintenance scheduling and fault alerts. - Compatible with existing ATM hardware/software. - Modular and scalable for future integration. | Value - Minimizes ATM downtime and improves customer satisfaction. - Meets SLA compliance goals and reduces manual efforts. - Increase operational efficiency and reduce support cost. - Supports regulatory compliance, service transparency and business KPIs. |

Document 3: User stories

| User Story No.: US001 | Tasks: 03 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Helpdesk Engineer, I want to receive real-time alerts for ATM failures So that I can act quickly to resolve issues and reduce downtime. |  |  |  |
| BV: 30 |  | CP: 05 |  |
| Acceptance Criteria: - Alerts should be generated within 30 sec of ATM failure. - Alert should include ATM ID, location and error code. - Ticket auto generated in service portal. |  |  |  |

| User Story No.: US002 | Tasks: 03 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Project Manager, I want to track ATM installation progress by location, so that I can ensure deadlines are met and vendors are performing. |  |  |  |
| BV: 40 |  | CP: 03 |  |
| Acceptance Criteria: - Track installation steps (Site ready → Installed → Activated). - Must support filtering by region and vendor. - Export should be accurate and downloadable. |  |  |  |

| User Story No.: US003 | Tasks: 03 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As an Operations Lead, I want to monitor SLA compliance of maintenance vendors, so that I can ensure service quality and take corrective action |  |  |  |
| BV: 30 |  | CP: 08 |  |
| Acceptance Criteria: - SLA threshold set per ticket type. - SLA breach highlights in red with timestamp. - Email notification sent to vendor and lead. |  |  |  |

| User Story No.: US004 | Tasks: 03 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Field Service Technician, I want automated ticket creation from alerts, so that I don’t miss urgent ATM issues. |  |  |  |
| BV: 50 |  | CP: 05 |  |
| Acceptance Criteria: - Ticket must auto-fill ATM ID, error, location, and timestamp. - Status updates must reflect in real-time. - Must be accessible via mobile. |  |  |  |

| User Story No.: US005 | Tasks: 03 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Compliance Officer, I want monthly reports on ATM service metrics, so that I can ensure we meet internal compliance standards |  |  |  |
| BV: 60 |  | CP: 08 |  |
| Acceptance Criteria: - Report includes metrics: downtime %, SLA met/missed, open/closed tickets. - Must be scheduled monthly. - Report must be exportable and tamper-proof (PDF with timestamp). |  |  |  |

Document 4: Agile PO Experience

The Product Owner has a vision of the product keeping the domain/industry experience and the market need.

The following are the responsibilities of PO in a project:

- Market Analysis:-

- Conducted market analysis to identify gaps in ATM lifecycle management, especially around real time fault handling and SLA tracking.

- Evaluated the availability of similar products, including tools used by banks and managed service providers.

- Identified that most solutions lack centralized visibility across installation, maintenance, and compliance.

- Enterprise Analysis:-

- Performed due diligence on the opportunity to reduce ATM downtime, optimize vendor management, and increase regulatory compliance.

- Worked closely with business stakeholders and field teams to assess the ROI potential of a centralized monitoring system.

- Product Vision and Roadmap:-

- Defined a clear product vision: “To build a unified platform that offers full control and visibility over ATM services from installation to maintenance across the Global TIS network.”

- Created a product roadmap with high-level features such as:

- ATM Installation Tracker

- Real-time Fault Monitoring

- SLA Compliance Dashboard

- Vendor Ticketing System

- Performance Reports Module

- Planned delivery across 5 major sprints over 6 months.

- Managing Product Features:-

- Prioritized features based on:

- Operational criticality (e.g., fault alerting)

- Business value (e.g., SLA metrics reporting)

- Ease of implementation

- Managed and balanced stakeholder expectations, including IT, Operations, Vendors, and Compliance Teams.

- Managing Product Backlog:-

- Continuously groomed and prioritized the Product Backlog.

- Reprioritized stories during sprint reviews based on stakeholder feedback and sprint performance.

- Broke down epics like “ATM Monitoring” into granular user stories such as “real-time alert for critical fault.”

- Managing Overall Iteration Progress:-

- Conducted regular Sprint Reviews to validate increments.

- Collaborated with the Scrum Master and Business Analyst to perform retrospectives and identify process improvements.

- Reprioritized stories and features in upcoming sprints based on dependencies and business urgency.

From this project I have learned how to handle sprint meetings such as:

- Sprint Planning Meeting – Defined sprint goals, committed user stories, and assigned tasks.

- Daily Scrum Meeting – Monitored progress, addressed blockers, and coordinated among developers.

- Sprint Review Meeting – Presented deliverables to stakeholders and gathered feedback.

- Sprint Retrospective Meeting – Evaluated sprint success, identified improvement actions.

- Backlog Refinement Meeting – Refined epics into stories, added BV and CP, and maintained clarity.

User Story Creation Experience:

- Story Number (e.g., US001)

- Tasks (in numeric format for planning)

- Priority (High, Medium, Low)

- Acceptance Criteria (detailed testable conditions)

- BV (Business Value) & CP (Complexity Point) (for ROI-based prioritization)

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog:-

- A Product Backlog is a prioritized list of all features, enhancements, bug fixes, technical work, and knowledge acquisition needed to deliver a product. It is owned by the Product Owner and evolves throughout the project.

- It includes high level items like epic, features and user stories that reflect the entire scope of the project.

| User Story ID | User Story | Task | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US001 | As a Helpdesk Engineer, I want to receive real-time alerts for ATM failures So that I can act quickly to resolve issues and reduce downtime. | 03 | High | 30 | 05 | Sprint-1 |
| US002 | As a Project Manager, I want to track ATM installation progress by location, so that I can ensure deadlines are met and vendors are performing. | 03 | Medium | 40 | 03 | Sprint-1 |
| US003 | As an Operations Lead, I want to monitor SLA compliance of maintenance vendors, so that I can ensure service quality and take corrective action. | 03 | High | 30 | 08 | Sprint-1 |
| US004 | As a Field Service Technician, I want automated ticket creation from alerts, so that I don’t miss urgent ATM issues. | 03 | High | 50 | 05 | Sprint-1 |
| US005 | As a Compliance Officer, I want monthly reports on ATM service metrics, so that I can ensure we meet internal compliance standards. | 03 | Medium | 60 | 08 | Sprint-1 |

Sprint Backlog:-

- A Sprint Backlog is a subset of the product backlog, selected during Sprint Planning, that the team commits to deliver in the current sprint.

- It includes selected user stories, task to complete those stories, effort estimates, daily updates during the sprint.

| User story ID | User Story | Task | Owner | Status | Estimated efforts |
| --- | --- | --- | --- | --- | --- |
| US001 | Register a new ATM location | Form design, backend integration, UI testing | Divya | In-progress | 5 |
| US002 | Track ATM installation status | Build status module, link to DB, test | Sunil | In-progress | 8 |
| US003 | Raise issues via support form | Create form, set up backend logic, email alerts | Kavita | In-progress | 3 |

Document 6: Sprint meetings

Meeting Type 1: Sprint Planning meeting

| Field | Details |
| --- | --- |
| Date | 10 july 2025 |
| Time | 10:00 AM- 11:00 AM |
| Location | Teams |
| Prepared By | Roopshree S. |
| Attendees | Webster Britney, Russ Micheal, Oliveria Joao, S Umesh, Vipul Sharma, Oliveria Joao, Divya Nayak, Neha Shinde, Saurabh D., Kavita Bagle, Sunil More |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Sprint Goal Finalization | Product Owner | 20 mins |
| Review of User Stories & Estimation | Scrum Team | 40 mins |
| Sprint Backlog Confirmation | Scrum Master | 20 mins |

Other Information

| Item | Details |
| --- | --- |
| Observers | QA Manager, Business Analyst |
| Resources | Jira board, confluence, sprint backlog document |
| Special Notes | Focus on prioritizing ATM software installation module in this sprint. |

Meeting Type 2: Sprint review meeting

| Field | Details |
| --- | --- |
| Date | 10 july 2025 |
| Time | 10:00 AM- 11:00 AM |
| Location | Teams |
| Prepared By | Roopshree S. |
| Attendees | Webster Britney, Russ Micheal, Oliveria Joao, S Umesh, Vipul Sharma, Oliveria Joao, Divya Nayak, Neha Shinde, Saurabh D., Kavita Bagle, Sunil More |

| Sprint Status | Things to Demo | Quick Updates | What’s Next |
| --- | --- | --- | --- |
| Sprint completes 90% scope | ATM software setup module, PIN generation interface | Minor bugs in card reader config, resolved | Begin installation module with ATM location tracking setup |

Meeting Type 3: Sprint retrospective meeting

| Field | Details |
| --- | --- |
| Date | 10 july 2025 |
| Time | 10:00 AM- 11:00 AM |
| Location | Teams |
| Prepared By | Roopshree S. |
| Attendees | Webster Britney, Russ Micheal, Oliveria Joao, S Umesh, Vipul Sharma, Oliveria Joao, Divya Nayak, Neha Shinde, Saurabh D., Kavita Bagle, Sunil More |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint 1 review | Timely delivery of PIN module and UI integration | ATM location services integration was delayed | Can we avoid external dependency bottleneck? | Sprint board, jira board |
| Improvement | Great coordination among Dev &QA | Daily stand-up exceeded timebox | Can we assign a timekeeper in each stand-up | Retrospective action list |

Meeting Type 4: Daily Stand-up meeting:

| Question | Name | Week (7-7-25 to 11-7-25) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun |
| What did you do yesterday? | Divya | Complete login API | Fixed minor UI bugs | Code review of Story #2 | Finalized data models | Wrote unit test for story #3 |  |  |
|  | Sunil | Researched new reporting plugin | Drafted report module wireframes | Integrated analytics dashboard | Team sync & retrospective | Helped QA with bugs |  |  |
|  | Saurabh | Setup development environment | Started story- backend | Created SQL schema | Backend API testing | Assisted in release planning |  |  |
| What will you do today? | Divya | Start Story #3 frontend | Debug data-binding issue | Collaborating with Designer | Implement login validation. | Prepare sprint demo |  |  |
|  | Sunil | Create report filters UI. | Fix CSS issues | Build test cases | Merge PR to dev branch | Complete documentation |  |  |
|  | Saurabh | Finish backend logic for Story #4 | API testing & validation | Assist Dev 2 with UI alignment | Dependency on backend fix | Run final regression test |  |  |
| What (if any) is blocking your progress? | Divya | Awaiting feedback from UX team | - | - | Dependency on backend fix |  |  |  |
|  | Sunil | Waiting for data model confirmation | - | Need final approval on reports layout | - |  |  |  |
|  | Saurabh | Access issues to QA server | - | - | - | Need test credentials from DevOps |  |  |