## Slide 1: Development And Implementation of Retort Sterilization Application
For Tastybite India
Prepared By- Tushar Musale Date- 07-01-2025

## Slide 2: Introduction
Tasty Bite offers convenient, ready-to-eat, and flavorful Indian and Asian-inspired meals. Their product range includes ready-to-serve rice, curries, and lentils, made with high-quality, natural ingredients.
Tastybite India aims to enhance its retort sterilization process by implementing an automated system to improve efficiency, ensure regulatory compliance, and maintain product quality.

## Slide 3: Situation / Problem-
Tastybite India currently lacks an automated and integrated system to monitor, control, and document the sterilization process in retort machines.
This manual approach is time-consuming, prone to errors, and inefficient in meeting regulatory compliance standards.

## Slide 4: Purpose Statement (Goals):
The purpose of this project is to analyze, design, and implement a Retort Sterilization Application to enhance operational efficiency, ensure regulatory compliance, and improve product quality through automation and real-time monitoring

## Slide 5: Project Objectives
Automated Process Control: Implement a solution to control and monitor sterilization cycles precisely.
Data Logging and Traceability: Ensure comprehensive data recording for regulatory compliance and audits.
User-friendly Interface: Provide an interactive dashboard for operators and supervisors.
System Integration: Enable seamless integration with hardware (PLCs, IoT devices) and enterprise systems (ERP, LIMS).
Compliance Adherence: Meet FDA, WHO, and other relevant regulatory standards.

## Slide 6: Key Features
Automated control of sterilization cycles.
Real-time monitoring of temperature, pressure, and time.
Recipe management for customized cycles.
Alarms and notifications for deviations.
Comprehensive reporting and analytics.

## Slide 7: Success Criteria
Enhanced Data Accessibility: Improve availability and accessibility of sterilization cycle records, logs, and reports.
Improved Efficiency: Ensure faster cycle processing and reduced manual data logging errors.
Regulatory Compliance: Successfully pass regulatory audits with the system-generated reports.
User Adoption: Achieve 90% user satisfaction based on post-implementation surveys.

## Slide 8: Project Approach
Requirement Analysis: Gather inputs from stakeholders and define specifications.
Operators: Understand pain points in the current process.
QA Teams: Identify data requirements for compliance.
Regulatory Experts: Ensure all compliance standards are addressed.
Develop a comprehensive Requirements Specification Document:
Functional requirements: Cycle programming, alarms, reporting.
Non-functional requirements: Performance, security
Integration requirements: Hardware ( IoT devices) and software (ERP/LIMS).
Solution Design: Evaluate vendors and finalize system architecture.
Development: Build and test application features and integrations.
Implementation: Deploy the system and provide user training.
Go Live: Launch the application and monitor the performance

## Slide 9: Project Approach
2. Solution Design and Selection
Evaluate existing solutions through an RFP process.
Select vendors based on:
  Compliance capability.
  Integration flexibility.
  User-friendliness and scalability.
Finalize the system architecture:
  Frontend: Operator dashboard, admin panel.
  Backend: Process control, data storage, reporting.
  Database: Structured schema for batch data and historical logs.

## Slide 10: Project Approach
3. Prototyping and Development
Build prototypes for critical features:
  Process control module.
  Real-time monitoring and alarms.
  Reporting interface.
Develop and integrate:
  Frontend, Backend Database: Design schemas for batch data, cycle logs, and audit trails.
Test developed features in a controlled environment

## Slide 11: Project Approach
4. Implementation and Training
Deploy the system in a phased manner:
  Pilot implementation on one retort machine.
Train stakeholders:
  Operators: On using the new dashboard and alarms.
  Technical Staff: On troubleshooting and maintenance.
5. Go Live
Conduct final validation tests with all stakeholders.
Launch the system and monitor performance for a defined stabilization period

## Slide 12
Resources:
Project Team:
Business Analyst (Requirement gathering, design documentation).
Developers (Frontend, backend, database, integration).
QA Testers (Validation and compliance testing).
Project Manager (Overall coordination).
Business Stakeholders-
Project team members from Tastybite India (operations, QA, IT teams).
External consultants for system integration.

## Slide 13
Time:
Project implementation within 5 months max.
1 month for requirement gathering.
0.5 months for design.
2 months for development and prototyping.
1 month for testing and training.
0.5 months for deployment and stabilization.
Budget:
Estimated Costs:25,00,000
Hardware: Rs. 12,00,000.
Software licenses: Rs. 3,00,000.
Development, Training and Services: Rs. 10,00,000

## Slide 14: Project Timeline
Phase | Duration
Requirements Gathering | 1 month
Design and Selection | 0.5 months
Development | 1.5 months
Testing and Training | 1 month
Deployment and Go-Live | 0.5 months
Total Duration | 5 months

## Slide 15: Risks and Dependencies
• Transition challenges due to familiarity with the current manual system.
• Dependencies on timely hardware integration and stakeholder collaboration.

## Slide 16: Deliverables Summary
Requirements Specification Document
System Design Document
Prototype and Pilot Implementation
Training Manuals(operational)
Final Application with Documentation
Compliance Reports

## Slide 17: Conclusion
The Retort Sterilization Application will revolutionize Tastybite India's sterilization process by enhancing efficiency, ensuring compliance, and maintaining product quality.