Q.1. Document 1: Definition of Done

Ans. Definition of Done is a shared checklist that ensures a backlog item is complete and meets quality standards. For IDSCD, the DoD includes:

- Acceptance criteria met for each dashboard feature (e.g., compliance alerts, audit logs)

- Code developed and deployed in a test environment identical to production

- Unit tests written and passed for each module

- UX design approved for wireframes (Balsamiq)

- QA testing completed and issues resolved

- Peer code review performed

- Documentation updated (RTM, user guides)

- Product Owner sign-off after sprint review

- Refactoring completed for optimized performance

- Configuration changes documented

Q.2. Document 2- Product Vision

Ans.

| Scrum Project Name: IDSCD – Integrated Drug Safety & Compliance Dashboard |  |  |  |  |
| --- | --- | --- | --- | --- |
| Venue: Abbvie Health Virtual Lab, Hyderabad |  |  |  |  |
| Date: 01 August 2025 |  | Start time: 10:00 AM | End time: 12:30 PM | Duration: 2 hours 30 minutes |
| Client: Medline India |  |  |  |  |
| Stakeholder list: PV Analysts Regulatory Affairs Team QA Managers IT Support Team Product Owner Scrum Master |  |  |  |  |
| Scrum Team |  |  |  |  |
| Scrum Master: Mr. Ramesh Kumar |  |  |  |  |
| Product owner: Isha Joshi |  |  |  |  |
| Scrum Developer 1: Priya Sharma |  |  |  |  |
| Scrum Developer 2: Arjun Mehta |  |  |  |  |
| Scrum Developer 3: Sneha Patil |  |  |  |  |
| Scrum Developer 4: Rahul Deshmukh |  |  |  |  |
| Scrum Developer 5: Kavita Joshi |  |  |  |  |
| Vision: To build a centralized, real-time dashboard that enhances pharmacovigilance operations, ensures regulatory compliance and streamlines adverse event tracking for Medline India. |  |  |  |  |
| Target group Pharmaceutical safety teams, regulatory officers and internal QA departments. | Needs 1. Real-time visibility into adverse event cases 2. Automated compliance alerts 3. Audit-ready documentation and logs 4. Integration with legacy PV systems |  | Product A web-based dashboard with modular features including AE tracking, compliance alerts, audit logs and reporting tools. | Value 1. Strengthens regulatory governance 2. Reduces manual workload 3. Improves ROI through operational efficiency 4. Positions Medline India as a tech-enabled PV leader |

Q.3. Document 3: User stories

Ans.

| User story No: US-001 |  | Tasks: 2 (Design AE intake module, integrate with legacy PV system) | Priority: High |
| --- | --- | --- | --- |
| Value statement: As a PV analyst, I want to view real-time AE case metrics so that I can detect safety signals faster. |  |  |  |
| BV: 500 | CP: 13 |  |  |
| Acceptance criteria: - AE data auto-populates from intake sources - Dashboard displays severity, country and report date - Filters available for signal detection |  |  |  |

| User story No: US-002 |  | Tasks: 3 (View AE case metrics, filter cases by severity and country, generate signal detection reports) | Priority: High |
| --- | --- | --- | --- |
| Value statement: As a PV Analyst, I want to access real-time adverse event data so that I can detect safety signals quickly and report them efficiently. |  |  |  |
| BV: 200 | CP: 08 |  |  |
| Acceptance criteria: - Dashboard displays AE count, severity and country - Filters allow sorting by date and drug name - Exportable reports available in PDF/Excel format |  |  |  |

| User story No: US-003 |  | Tasks: 3 (Monitor compliance timelines, receive alerts for overdue submissions and access audit logs) | Priority: High |
| --- | --- | --- | --- |
| Value statement: As a Regulatory Affairs Officer, I want automated alerts for compliance deadlines so that I can ensure timely submissions and avoid penalties. |  |  |  |
| BV: 500 | CP: 13 |  |  |
| Acceptance criteria: - Alerts triggered 7 days before due dates - Dashboard shows submission status - Audit logs are timestamped and downloadable |  |  |  |

| User story No: US-004 |  | Tasks: 3 (Review dashboard modules for quality, validate data accuracy and approve release readiness) | Priority: Medium |
| --- | --- | --- | --- |
| Value statement: As a QA Manager, I want to validate dashboard functionality so that I can ensure it meets quality standards before deployment. |  |  |  |
| BV: 100 | CP: 05 |  |  |
| Acceptance criteria: - QA checklist completed for each module - Bugs tracked and resolved in JIRA - Final sign-off documented |  |  |  |

| User story No: US-005 |  | Tasks: 3 (Manage backend integration, ensure uptime and performance, provide technical support | Priority: Medium |
| --- | --- | --- | --- |
| Value statement: As an IT Support Engineer, I want to monitor system performance so that I can ensure the dashboard runs smoothly without downtime. |  |  |  |
| BV: 200 | CP: 20 |  |  |
| Acceptance criteria: - System uptime ≥ 99% - API integrations tested and stable - Support tickets resolved within SLA |  |  |  |

| User story No: US-006 |  | Tasks: 3 (Prioritize backlog items, review sprint outcomes and align features with business goals) | Priority: High |
| --- | --- | --- | --- |
| Value statement: As a Product Owner, I want to manage the product roadmap so that I can deliver high-value features aligned with stakeholder needs. |  |  |  |
| BV: 500 | CP: 08 |  |  |
| Acceptance criteria: - Backlog items prioritized using MoSCoW - Sprint reviews conducted with stakeholders - Roadmap updated after each sprint |  |  |  |

| User story No: US-007 |  | Tasks: 3 (Elicit requirements, create wireframes and RTM, facilitate sprint planning) | Priority: High |
| --- | --- | --- | --- |
| Value statement: As a Business Analyst, I want to document requirements and create wireframes so that the development team can build features accurately. |  |  |  |
| BV: 200 | CP: 08 |  |  |
| Acceptance criteria: - Wireframes approved by stakeholders - RTM maps all requirements to features - Sprint planning includes BA inputs |  |  |  |

Q.4. Document 4: Agile PO Experience

Ans. Product Owner Responsibilities in IDSCD:

- Market Analysis: Identified need for centralized PV dashboards in pharma

- Enterprise Analysis: Compared existing tools and gaps in compliance tracking

- Product Vision: Defined modular dashboard with real-time metrics

- Roadmap: Planned 4 sprints with feature-based delivery

- Feature Management: Prioritized AE tracker, compliance alerts, audit logs

- Backlog Management: Created and refined user stories with BA

- Iteration Progress: Reviewed sprint outcomes, reprioritized based on feedback

- Sprint Meetings: Participated in planning, review, retrospective and backlog grooming

- The product owner also looks into the user stories creation and what things will be included in user stories such as story no, tasks, priority, acceptance criteria, BV & CP value.

- In Scrum, a product owner serves as the liaison between multiple areas of an organization, communicates with business stakeholders and collaborates closely with scrum teams to keep all areas of the business informed on a project's development.

- The product owner develops a vision of a product's function and operation, which in turn allows the scrum team members to define product features and break those features into product backlog items.

Q.5. Document 5: Product and sprint backlog and product and sprint burndown charts

Ans. Product backlog:

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US-001 | AE Intake Module | Design UI, integrate DB | High | 500 | 08 | Sprint 1 |
| US-002 | PV Analyst Dashboard | View AE metrics, filter cases, generate reports | High | 500 | 08 | Sprint 1 |
| US-003 | Requirement Elicitation & Wireframes (BA) | Conduct workshops, create RTM, design wireframes | High | 500 | 08 | Sprint 1 |
| US-004 | Compliance Alert System | Set alert rules, configure timelines, test notifications | High | 500 | 13 | Sprint 2 |
| US-005 | Audit Log Dashboard | Create log structure, enable export, timestamp entries | Medium | 200 | 05 | Sprint 2 |
| US-006 | Regulatory Affairs Dashboard | Monitor timelines, receive alerts, access logs | High | 500 | 13 | Sprint 2 |
| US-007 | Role-Based Access Module | Define roles, assign permissions, test login flows | Medium | 200 | 08 | Sprint 3 |
| US-008 | QA Validation Workflow | QA checklist, bug tracking, release approval | Medium | 200 | 05 | Sprint 3 |
| US-009 | IT Performance Monitoring | Backend integration, uptime tracking, support ticketing | Medium | 200 | 20 | Sprint 3 |
| US-010 | Product Roadmap Management (PO) | Prioritize backlog, review sprints, update roadmap | Low | 100 | 08 | Sprint 4 |

Sprint backlog:

| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US-001 | AE Intake Module | Design UI, integrate DB, test data flow | Scrum Dev 1 | Work In Progress | 8 hours |
| US-002 | PV Analyst Dashboard | Create filters, build metrics view, enable export | Scrum Dev 2 | Not Started | 10 hours |
| US-003 | Regulatory Affairs Dashboard | Build submission tracker, integrate alerts, enable audit access | Scrum Dev 2 | Not Started | 13 hours |
| US-004 | Compliance Alert System | Configure alert rules, test notifications, validate timelines | Scrum Dev 3 | Work In Progress | 13 hours |
| US-005 | QA Validation Workflow | Create QA checklist, bug tracking setup, release approval flow | Scrum Dev 3 | Not Started | 05 hours |
| US-006 | Audit Log Dashboard | Design log structure, enable export, timestamp entries | Scrum Dev 4 | Done | 05 hours |
| US-007 | IT Performance Monitoring | Backend integration, uptime tracking, support ticketing setup | Scrum Dev 4 | Work In Progress | 20 hours |
| US-008 | Role-Based Access Module | Define roles, assign permissions, test login flows | Scrum Dev 5 | Work In Progress | 08 hours |
| US-009 | Product Roadmap Management (PO) | Prioritize backlog, review sprint outcomes, update roadmap | Product Owner | Work In Progress | 08 hours |

Product burndown chart:

Tracks overall progress across sprints

Sprint burndown chart:

Daily effort vs. remaining work visualized for each sprint

Q.6. Document 6: Sprint meetings

Ans. Meeting Type 1: Sprint Planning meeting

| Date | 01-Aug-2025 |
| --- | --- |
| Time | 10 AM |
| Location | Abbvie Health Virtual Lab, Hyderabad |
| Prepared By | Mr. Ramesh Kumar |
| Attendees | Scrum master, product owner, Scrum developers, Quality analyst |

Agenda topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Welcome and Meeting Objectives | Scrum Master | 5 mins |
| Review Product Vision | Product Owner | 10 mins |
| Review Sprint Goal | Product Owner | 10 mins |
| Task Breakdown and Estimation | Scrum Developers | 20 mins |
| Capacity Planning | Scrum Master | 10 mins |
| Sprint Commitment | Entire Scrum Team | 10 mins |

Other Information

| Observers | QA Lead, UX Designer, Project Sponsor |
| --- | --- |
| Resources | JIRA (Sprint Backlog & Burndown Charts), Balsamiq (Wireframes), Visio (UML) |
| Special Notes | Ensure all user stories meet Definition of Done; UX and QA sign-off required |

Meeting Type 2: Sprint review meeting

| Date | 15-Aug-2025 |
| --- | --- |
| Time | 11 AM |
| Location | Abbvie Health Virtual Lab, Hyderabad |
| Prepared By | Mr. Ramesh Kumar |
| Attendees | Product Owner, Scrum Master, Scrum Developers, QA Lead, UX Designer |

| Sprint status | Things to demo | Quick updates | What’s next |
| --- | --- | --- | --- |
| AE module completed | Dashboard prototype | Minor UI tweaks pending; backend validation in progress | Begin Sprint 2 (Compliance Alerts) |

Meeting Type 3: Sprint retrospective meeting

| Date | 16-Aug-2025 |
| --- | --- |
| Time | 11 AM |
| Location | Abbvie Health Virtual Lab, Hyderabad |
| Prepared By | Mr. Ramesh Kumar |
| Attendees | Product Owner, Scrum Master, Scrum Developers, QA Lead, UX Designer |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint Retrospective | Clear communication, timely delivery | Initial DB integration delays | How can we improve backend coordination? | Agile Deliverables – V2D2 |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week “1” (from 01-08-2025 to 05-08-2025) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday |
| What did you do today? | Dev 1 | Designed AE Intake UI | Integrated AE DB | Tested AE module | Started Compliance Alert logic | Completed Compliance Alert notifications |
|  | Dev 2 | Created PV Dashboard filters | Built metrics | Enabled export to Excel | Started Regulatory Dashboard | Integrated alert triggers |
|  | Dev 3 | Set up QA checklist | Logged bugs in JIRA | Validated AE module | Started Role-Based Access module | Assigned permissions |
| What will you do tomorrow? | Dev 1 | Integrate AE DB | Test AE module | Start Compliance Alert logic | Complete alert logic | Review Audit Log structure |
|  | Dev 2 | Build metrics view | Enable export | Start Regulatory Dashboard | Integrate alert triggers | Review submission tracker |
|  | Dev 3 | Log bugs in JIRA | Validate AE module | Start Role-Based Access module | Assign permissions | Test login flows |
| What (if any) is blocking your progress? | Dev 1 | None | API delay | None | Minor DB sync issue | None |
|  | Dev 2 | None | None | Delay in alert logic | None | None |
|  | Dev 3 | None | None | Waiting for access credentials | None | None |