## Slide 1: Financial Crime Risk
Project Title : Removal of booking country from application
Prepared By : Anjali Mehta
Date : 03/03/2025

## Slide 2: Executive Summary
As part of HSBC’s strategic exit from Canada, this project aims to fully remove Canada as a booking country from the Financial Crime Risk (FCR) system. This will ensure HSBC remains compliant with global data governance standards while improving operational efficiency for investigators and streamlining system performance.
By following an Agile approach, the project will:
Identify and remove all Canadian data, rules, and configurations within FCR.
Ensure regulatory compliance (PIPEDA, HSBC Data Governance).
Safeguard global processes through comprehensive testing and validation.
Deliver cleaner, faster investigations for other booking countries.
This project reduces risk, improves compliance, and aligns with HSBC’s simplification strategy, delivering both regulatory and operational value.

## Slide 3: Project Background
Why is this important for HSBC?
HSBC has announced its exit from retail banking in Canada, impacting 14,000+ accounts.
FCR was originally configured to actively monitor Canadian transactions and accounts, which is no longer needed.
Failure to remove Canada could result in:
  False risk alerts, adding noise to investigator workloads.
  Compliance breaches due to unnecessary data retention.
  Higher operational costs to manage redundant rules and data.
This project aligns with HSBC’s global strategic focus on simplification and operational efficiency.

## Slide 4: Proposed Solution
Conduct a full data, rules, and process discovery for Canada within FCR.
Identify and remove all Canada-specific:
Client records
Account data
Payment's history
GTRF transactions
Risk rules & screening logic
Reference data (country codes, currency mappings, etc.)
Country-specific reports & dashboards
Work with Data Governance to archive any data required for regulatory retention periods.
Update global configurations to ensure no residual impact on global processes.
Conduct end-to-end regression testing to protect global functionality.
Document all changes for audit readiness.

## Slide 5: Situation
The Financial Crime Risk (FCR) application is a core compliance tool used at HSBC to monitor transactions and customer activity across 14 booking countries, including Canada. Due to strategic shifts, regulatory realignment, and restructuring, HSBC has decided to exit the Canadian market for certain products and services covered by FCR.
As part of this strategic decision, Canada must be completely removed from the FCR system to avoid unnecessary processing, ensure data privacy compliance (aligning with GDPR and compliance policies where applicable), and optimize system performance by removing redundant data pipelines and configurations.

## Slide 6: Problems
Redundant Data Processing: FCR continues to process transactions, accounts, and client data related to Canada, despite the market exit.
Compliance & Privacy Risks: Retaining unnecessary Canadian data could trigger data retention and privacy violations under GDPR and internal data governance policies.
Operational Inefficiency: Investigators are presented with alerts and insights from Canada, creating unnecessary noise and reducing productivity.
Rule Complexity: Screening rules for Canada add complexity to global configuration and increase maintenance overhead.

## Slide 7: Opportunity
By removing Canada as a booking country from FCR, HSBC can:
Streamline Compliance Operations: Investigators will no longer need to filter out Canadian cases.
Enhance System Performance: Data processing loads, and storage requirements will reduce.
Improve Data Governance: Canadian data can be decommissioned following approved retention policies, ensuring privacy compliance.
Simplify Rule Management: Removing Canada-specific rules will simplify the global screening configuration.
Reduce False Positives: Alerts triggered by Canadian accounts (which are no longer relevant) will be eliminated.

## Slide 8: Purpose
This project aims to safely and completely remove Canada from FCR, including:
Decommissioning Canadian client data, accounts, transactions, and GTRF information.
Removing Canada-specific rules, risk parameters, data feeds, and configurations.
Ensuring compliance with HSBC’s global data governance policy and regulatory retention obligations.
Validating that no operational processes, dashboards, or reports are negatively impacted post-removal.

## Slide 9: Project Objectives
Objective | Description
Specific | Remove all Canada-related data, rules, configurations, and dashboards from FCR.
Measurable | Confirm 100% removal through data reconciliation reports and system audits.
Achievable | Follow HSBC’s standard decommissioning playbook and data governance guidelines.
Realistic | Canada market exit is already an approved strategic decision.
Time-Bound | Complete within 3 months using Agile sprints (2-week cycles).

## Slide 10: Success Criteria
No Canada-related alerts, cases, or data remain in FCR post-implementation.
Canada-specific rules, screening logic, and reference data fully removed.
No adverse impact on global risk scoring, dashboards, or compliance processes.
Full audit trail demonstrating compliant data removal and system change controls.
Positive sign-off from key stakeholders: Compliance, Risk, Operations, and Technology.

## Slide 11: Methods/Approach
Sprint Phase | Key Deliverables
Sprint 0 | Discovery - Confirm Canada footprint in FCR (data, rules, dashboards, reports)
Sprint 1-2 | Removal of Canada-specific rules, configurations, and data feeds
Sprint 3-4 | Data extraction (if retention needed) + physical data removal
Sprint 5 | Full regression testing - ensure global functionality not impacted
Sprint 6 | Compliance review, UAT, and final sign-off
Post Go-Live | Monitor for 2 weeks, ensure no unexpected alerts, data issues

## Slide 12
Daily Standups for progress tracking.
Bi-weekly Sprint Reviews to capture stakeholder feedback.
JIRA for backlog & task management.
Confluence for process documentation.

## Slide 13: Deliverables
Deliverable | Description
Canada Data Removal Report | Confirm all Canadian data fully removed
Updated System Configuration | No Canada-specific rules, data feeds, or dashboards
Compliance Sign-off | Approval from Compliance, Legal, and Risk
Updated Process Documentation | Revised SOPs, process maps, and training guides
Post-Implementation Monitoring Report | Confirm stability & absence of residual issues

## Slide 14: Resources
Resources | Role
Business Analyst | Anjali mehta (Requirement gathering, process mapping, impact analysis)
Product Owner | Owns backlog prioritization & ensures alignment with compliance goals
Data Analyst | Assists with data profiling, extraction, and reconciliation
Developers | Update configurations, remove rules, adjust data pipelines
Testers | Validate system changes, conduct regression testing
Compliance SMEs | Confirm regulatory impacts and sign-off on data removal
Data Governance Team | Ensure compliant decommissioning (PIPEDA, HSBC policies)

## Slide 15: Risks and Dependencies
Risk/Dependency | Mitigation
Incomplete Data Discovery | Run comprehensive data lineage mapping in Sprint 0
Data Retention Conflicts | Early engagement with Legal & Data Governance teams
Configuration Dependencies | Dependency mapping before change implementation
Reporting Impact | Update global dashboards & reports as part of change scope
Audit Scrutiny | Maintain full documentation & approvals for all changes