## Slide 1: Project Title – Logistics Automation
Prepared By – Rohit Sarnaik
Date – 05/03/2025

## Slide 2: Situation
A retail company is struggling with frequent stock outs and overstocking in its warehouses due to inaccurate demand forecasting. This leads to lost sales, high storage costs, and poor customer satisfaction. Additionally, unpredictable supplier delays and inefficient logistics further disrupt the supply chain.

## Slide 3: Problem
Demand Forecasting Errors – Inaccurate predictions lead to stock outs or overstocking, increasing costs and reducing customer satisfaction.
Supply Chain Disruptions – Natural disasters, political instability, pandemics, or supplier failures can halt operations and delay shipments.
High Logistics Costs – Rising fuel prices, inefficient route planning, and last-mile delivery challenges increase transportation expenses.
Lack of Visibility & Tracking – Limited real-time monitoring of inventory, shipments, and supplier performance leads to inefficiencies.
Regulatory & Compliance Issues – Constantly changing trade regulations, tariffs, and environmental laws make global supply chain management complex.

## Slide 4: Opportunity
Cost Reduction – Optimizing inventory and logistics can lower storage and transportation costs
Improved Efficiency – Automating demand forecasting and supplier management can streamline operations.
Better Customer Satisfaction – Reduced stock outs and faster deliveries improve customer experience and loyalty.
Enhanced Supply Chain Resilience – Identifying risks and diversifying suppliers can minimize disruptions.
Sustainability & Compliance – Implementing eco-friendly practices can reduce waste and ensure regulatory compliance.
Competitive Advantage – Companies with a well-optimized supply chain can outperform competitors in speed and cost-effectiveness.

## Slide 5: Purpose Statement
The purpose of this project is to enhance supply chain efficiency by implementing data-driven strategies to optimize inventory management, reduce lead times, and improve demand forecasting. This project aims to minimize disruptions, lower operational costs, and enhance customer satisfaction by integrating advanced technologies like AI, IoT, and real-time tracking.
Additionally, it will focus on sustainability and regulatory compliance to ensure a resilient and future-proof supply chain system.

## Slide 6: Goals
Optimize Inventory Management – Reduce overstocking and stock outs through data-driven demand forecasting.
Enhance Supply Chain Visibility – Implement real-time tracking and monitoring of shipments, inventory, and supplier performance.
Improve Logistics Efficiency – Minimize transportation costs and delivery delays through better route planning and automation.
Increase Customer Satisfaction – Ensure product availability, faster deliveries, and better service levels.
Reduce Operational Costs – Streamline processes to lower warehousing, procurement, and transportation expenses.
Leverage Technology & Automation – Utilize AI, IoT, and blockchain for smarter decision-making and improved efficiency.

## Slide 7: Project Objectives
Improve Demand Forecasting Accuracy
Enhance Inventory Optimization
Increase Supply Chain Transparency
Lower Transportation Costs
Strengthen Supplier Collaboration
Increase Customer Satisfaction
Ensure Regulatory Compliance

## Slide 8: Success Criteria
Improved Forecast Accuracy
Inventory Optimization
Enhanced Supply Chain Visibility
Lower Transportation Costs
Increased Customer Satisfaction
Cost Reduction
Regulatory Compliance
Sustainability Impact

## Slide 9: Methods/Approach - Agile
Product Vision & Roadmap
  Define the long-term vision and high-level roadmap of the product.
  Business Requirements Gathering (Identify customer needs and market demands)
  Define major features & releases over time.
Sprint Planning
  Sprint Backlog (List of tasks for the sprint)
  Prioritize and refine product backlog (Use MoSCoW to prioritize tasks)
  Create Epics and breakdown epics into features and features into user story.
  Break down user stories into smaller tasks (Story Points, T-Shirt Sizing).
Incremental development & Testing
  Discuss progress, blockers, and next steps
  Deliver small, functional features in each sprint
  Unit tests, integration tests, and regression tests
  Ensure high-quality coding standards

## Slide 10
User Acceptance Testing (UAT)
  Conduct UAT with stakeholder to ensure efficiency and usability
  Gather feedback and iterate bases on user experience.
  Business owners sign off for deployment
Deployment & Go-Live
  Release new features
  Real-time monitoring and logging of issue
  Live system with continuous monitoring and user support

## Slide 11: Resources - People
Total Estimated Team Size – 10 -15 people
Project Management Team
Development Team
Database Administrator
Quality Assurance (QA) & Testing Team
UI/UX Design Team
Deployment & Support Team
Subject Matter Experts (SMEs)
External Consultants (If Required)

## Slide 12: Resources - Time
Phase | Duration | Task
Phase 1: Planning & Requirement Gathering | 2–3 weeks | Identify challenges, define objectives, create backlog, assign teams.
Phase 2: System & Process Analysis | 2–3 weeks | Conduct gap analysis, collect data, analyze inefficiencies.
Phase 3: Implementation & Development | 8-12 Weeks | AI-based demand forecasting, inventory tracking, logistics optimization.
Phase 4: Testing & Iteration | 4-6 Weeks | UAT, A/B testing, continuous improvements, sprint reviews.
Phase 5: Deployment & Monitoring | 4 Weeks | Deploy solutions, monitor KPIs, gather feedback.
Phase 6: Continuous Improvement & Scaling | 4 Weeks | Optimize processes, scale to other areas, finalize reports.
The total project duration is estimated to be 6 to 9 months, depending on the complexity and scale of implementation.

## Slide 13: Resources - Budget
The budget for the Logistics Automation project depends on factors such as team size, technology stack, hosting infrastructure, and maintenance costs. Below is a detailed budget breakdown, considering a mid-scale implementation over a 9-month timeline with ongoing support.
Estimated Total Budget: Rs 30,00,000 – Rs 60,00,000

## Slide 14: Resources - Other
Hardware & IT Infrastructure - 40,000 – 90,000
Software & Tools - 25,000 – 80,000
Logistics & Operational Resources - 55,000 – 135,000
Government & Legal Compliance Resources - 15,000 – 40,000
TOTAL OTHER RESOURCES BUDGET - 135,000 – 345,000
Apart from people, time, and budget, the project will require additional physical, technological, and operational resources to ensure successful execution and deployment. Below is a breakdown of other required resources

## Slide 15: Risks
Technical Risks
  Data Security & Cyber Threats
  Data Loss or Corruption
  System Performance Issues
Business & Operational Risks
  Supplier Disruptions
  Regulatory Compliance Issues
  Adoption Resistance
Financial Risks
  Project Budget Overruns
  Funding Shortages
  Payment Gateway Failures
External & Environmental Risks
  Economic Fluctuations
  Pandemics/Natural
  Geopolitical Instability

## Slide 16: Dependencies
Technology Dependencies
  AI/ML for Demand Forecasting
  ERP/WMS/TMS Integration
  IoT & RFID Tracking
  Cloud Infrastructure
Business & Stakeholder Dependencies
  Stakeholder Engagement
  Supplier & Vendor Cooperation
  Regulatory Compliance
  Change Management & Training
External Dependencies
  Market & Economic Conditions
  Third-Party Logistics (3PL)
  Data Availability & Accuracy
Financial Dependencies
  Budget Allocation
  Revenue Generation
Timeline Dependencies
  Delivery of Software Components
  User Training and On boarding
  Market Launch

## Slide 17: To Be Completed by Appropriate Manager
Project Sponsor - Logistics Automation
Project Manager - Jane Smith