## Slide 1: Delta Sales Operations Management Portal (SOMP)
Prepared By: Barath Narayanan
Role: Lead Business Analyst, Delta Healthcare
Date: 7th July 2025

## Slide 2: Executive Summary
This project aims to digitize and streamline all field sales operations into one unified portal.
Current manual processes hinder speed, accuracy, and transparency.
Success will mean faster decision-making, improved sales reporting, and operational efficiency.
Stakeholders will benefit from centralized data, real-time visibility, and reduced operational friction.

## Slide 3: Problem Statement
What problem are we solving?
Disjointed manual processes for meetings, quotations, leaves, expenses, and demo product requests.
Why does this matter?
It causes delays, errors, poor visibility, and inefficiencies in our national sales operation.
Impact if unresolved:
Missed opportunities, lack of scalability, and reduced competitiveness in customer service.

## Slide 4: Project Background
The problem has existed since Delta Healthcare scaled up its nationwide sales operations in 2019.
Sales reps use spreadsheets, WhatsApp, and calls for reporting, making data collection difficult.
This affects customer experience and slows down internal approvals.
Aligning this portal with our digital transformation goals will improve business agility.

## Slide 5: Stakeholder Expectations
Sales Team:
Easy and fast reporting, reduced manual paperwork.
Sales Heads/Managers:
Live dashboards, approval controls, historical data access.
Finance:
Accurate and timely expense claims.
HR:
Streamlined leave and travel request management.
IT:
Scalable, secure, and supportable solution.

## Slide 6: Project Goals (Purpose Statement)
Develop a secure, mobile-friendly, and scalable portal with integrated workflows for:
Daily meeting reports
Quotation generation
Leave and expense requests
Demo product and travel bookings
Empower managers with real-time access and analytics

## Slide 7: Proposed Solution
What:
Centralized portal built using web technologies with modular dashboards and workflow automation
Why it works:
Custom-built to Delta's operations with end-user feedback integrated
Better than alternatives:
Tailored design vs generic CRM tools; flexible workflows
Feasibility:
6-month phased implementation via Waterfall model

## Slide 8: Project Deliverables
Web-based sales portal (desktop & mobile)
Admin dashboard for approvals, analytics
Quotation generator with PDF output
Travel and leave request modules
Demo product request module
Expense claim form & tracker
User manual and training videos

## Slide 9: Success Criteria
The project is successful if:
100% of sales reps adopt portal within 3 months
Average reporting time drops by 50%
Quotation turnaround time improves from 2 days to 4 hours
Real-time tracking enabled for 100% of demo product movements
95% of users report ease of use (via feedback survey)

## Slide 10: SMART Objectives
Specific:
Digitize and automate all key sales field operations
Measurable:
Minimum 50% time savings in operations post-deployment
Achievable:
Within 6 months with internal and vendor collaboration
Realistic:
Built on standard tech stacks with moderate budget
Time-Bound:
Go-live by January 2026 with complete onboarding

## Slide 11: Project Approach – Waterfall Model
Requirement Gathering:
Stakeholder interviews, form approval matrices
System Design:
Workflow diagrams, UX/UI screens
Development:
Module-by-module build (back-end + front-end)
Testing:
Unit, integration, and UAT with pilot team
Training:
End-user training videos, helpdesk setup

## Slide 12: Project Team
Project Sponsor:
Mr. Ramesh Krishnan – Director, Sales & Operations
Project Manager:
Mr. Barath – Head, IT Systems
Business Analyst:
Mr. Barath
Frontend Developer:
Mr. Prashant Kapoor
Backend Developer:
Mr. Arvind Menon
QA Tester:
Mr. Shivaji Rao
Sales User Group:
Mr. Naveen Thomas
IT Support:
Mr. Manoj Verma

## Slide 13: Resource Requirements and Budget
People:
7 team members (listed in previous slide)
Timeline:
6 months (Jul 2025 – Jan 2026)
Budget Estimate: ₹24,50,000
Development: ₹12,00,000
Licenses & Tools: ₹3,00,000
Training & Support: ₹2,50,000
Testing & QA: ₹2,00,000
Contingency & Travel: ₹5,00,000

## Slide 14: Risks and Mitigations
Resistance to change:
Mitigated by training and early pilot feedback
Timeline slippage:
Strict milestone-based delivery with reviews
Integration delays:
Defined data formats and early IT coordination
Adoption challenges:
Incentives for early adoption, feedback loop
Security concerns:
Standard encryption, role-based access, backups

## Slide 15: Appropriate Managers
Project Sponsor
Name: Mr. Ramesh Krishnan
Designation: Director – Sales & Operations
Department: Business Development
Signature: [Signed]
Date: 07-07-2025
Project Manager
Name: Mr. Barath
Designation: Project Manager – IT Systems
Department: Information Technology
Signature: [Signed]
Date: 07-07-2025