## Slide 1
Project Title - Lab Optimization using Waterfall Model
Prepared By- Ashwini Khanvilkar
Date – 18/03/2025

## Slide 2
Situation :
The lab faced challenges in documentation, inventory management and overall operations.
Communication gaps between lab staff, engineers and patients led to misunderstandings.
Manual SOPs and inventory tracking slowed down efficiency.
Problem :
Manual Documentation – Important records like SOPs, patient files, and audit reports were stored in physical format, making them hard to find.
Inventory Mismanagement – No proper system to track stock, causing overstocking or shortages.
Communication Gaps – No structured way for lab staff, patients, and engineers to communicate.
Process Delays – Inefficient workflows increased turnaround time for lab processes.
Opportunity :
Convert SOPs and records into digital format for easy access and faster work.
Implement an inventory tracking system to manage stock in real-time.
Improve communication processes for better coordination.
Optimize workflows to meet NABL requirements and improve efficiency.

## Slide 3
Purpose Statement (Goals)
Reduce manual tasks and improve overall lab efficiency.
Digitize SOPs and ensure easy access for better compliance.
Enhance communication between lab staff, patients, and engineers for better coordination.
Implement a real-time inventory tracking system.
Improve NABL compliance by ensuring up-to-date documentation.
Minimize process delays and system downtime.
Standardize reporting and assessments to support better decision-making and overall lab performance.

## Slide 4
Project Objectives
Digitize all SOPs and maintain a centralized system for easy access.
Implement a real-time inventory tracking system to avoid shortages and wastage.
Establish clear communication protocols for better coordination between lab staff, patients, and engineers.
Compliance Readiness – Ensure all documentation aligns with NABL standards.
Optimize workflows to reduce turnaround time for lab results.

## Slide 5
Success Criteria
Improved Documentation Access – 100% of SOPs, compliance reports, and patient records stored digitally for easy retrieval.
Reduced System Downtime and Wait Times – Decrease downtime by 40%, ensuring faster and smoother lab processes.
Efficient Inventory Management – Reduce material wastage by 30% with real-time stock tracking and better resource planning.
Better Client Interaction – Increase communication efficiency by 50% through standardized processes between lab staff, patients, and engineers.
Optimized Lab Workflows – Cut down lab operation delays by 35%, ensuring faster report generation and improved efficiency.

## Slide 6
Methods/Approach
Phase 1: Requirement Gathering
Identify issues in SOP documentation, inventory tracking, and client communication.
Gather feedback from lab staff, engineers and patients.
Phase 2: System Design
Plan the digital transformation of SOPs and develop an inventory tracking system.
Define structured workflows for client communication and NABL compliance.
Phase 3: Development & Implementation
Set up a digital system for SOP documentation and audits.
Implement real-time inventory tracking.
Establish communication protocols.
Phase 4:Testing & Validation
Conduct pilot testing with selected lab staff and clients.
Ensure system accuracy and NABL compliance.
Make necessary improvements based on feedback.

## Slide 7
Phase: 5 Training and Deployment
Train lab employees and engineers on the new systems.
Conduct workshops on SOP digitization, inventory tracking, and workflow management.
Monitor performance and make continuous improvements.

## Slide 8
Resources
People :
Project Team: Developers, Business Analysts, Quality Analysts, Project Managers.
Lab Team: Lab Staff, Engineers, and IT Support.
Clients/End Users: Patients and Third-Party Evaluators.
Time :
Total - 6-7 months
Requirement Gathering – 1 – 1.5 months
System Design – 1 Month
Development & Implementation - 2 – 2.5 months
Testing & Validation - 1 month
Training & Deployment - 1 month
Budget :
Total Estimated Budget – ( ₹13.75 – ₹22.5 L)
Other :
Kanban Board, Timesheet, Change tracker, Third party evaluation, NABL Compliance Tools, Microsoft Excel / Google Sheets, Document Management System (DMS)

## Slide 9
Risks :
Lab staff may struggle to adapt to the new digital system, which can delay the process.
There is a chance of technical problems like system errors or slow performance, which can affect daily work.
If NABL rules are not followed correctly, the lab may face issues during audits.
Important data like patient records and SOPs need to be protected from security risks.
The new system may take time to fit into the existing lab process, causing delays.
If clients and evaluators ask for many changes, testing may take longer than planned.
Dependencies :
Collaboration between lab staff, engineers and IT teams.
Proper requirement gathering to ensure the system meets lab needs.
NABL compliance must be maintained for certification.
Training is essential for smooth adoption of the new system.
Regular feedback and updates for continuous improvement.

## Slide 10
Thank You
Project Sponsor- Aastha
Project Manager – Ashwini